## Admin Unit
School Admin Unit | Location | Date Record Updated | Assistance Requested | Report Tool PIN | PWS? | MWRA? | Phase 1? | # Schools | Date for IM | IM time | Primary TAP | Sample Plan | Date First Sampled | Laboratory | Total # Samples | Status? | DEP Region | TAP(s) at IM | Comments
AbingtonPS | ABINGTON | 2017-12-19 | Follow up | 9f3c-affa-4883 | N | N | Y | 1 | none needed |  |  | 0:1 |  | RI Analytical |  | Will send us map and Sample Plan | Southeast
AgawamPS | AGAWAM | 2018-06-08 | Full sampling | 4c48-1654-3b10 | N | N | N | 8 | 2018-03-09 | 9:30AM | BH | 8:8 |  |  | 668 | Fall sampling? | Western
Amesbury PS | AMESBURY | 2018-04-26 |  | 8ec8-1e09-055d | N | N | N | 5 | [7 empty] | Waiting list | Western
BaystateACPS | SPRINGFIELD | 2018-05-17 | Full sampling | 77a0-613f-ca49 | N | N | N | 1 | 2017-10-18 | 9:00AM | GB | 1:1 | 2018-03-31 | Eurofins | 26 | All Results sent | Western | GB, RL
BraintreePS | BRAINTREE | 2018-06-21 | Full sampling | f364-9b10-1331 | N | N | N | 10 | 2018-05-03 | 2:30PM | GB | 10:10 | 2018-06-12 | RI Analytical | 593 | All Results sent | Southeast
BRRSD | BRIDGEWATER | 2018-08-24 | Full sampling | 69b1-0b42-0241 | N | N | N | 7 | 2018-04-18 | 10:00AM | TB | 6:7 | 2018-06-19 | RI Analytical | 499 | All Results sent | Southeast
Canton Preschool | CANTON | 2018-04-27 | Out of Program | 224b-a826-d856 | N | N | N | 1 | Out of Program |  |  |  | Out of Program |  |  | Out of Program | Southeast |  | They say they are too busy to fit this in
CCCDP | HYANNIS | 2018-05-10 | Out of Program | ea12-e96d-92b9 | N | N | N | 11 | 2018-05-08 | 11:00AM | TB | 0:11 | Out of Program |  |  | IM completed | Southeast |  | No reason given
Children's Workshop | CUMBERLAND RI | 2018-06-29 | Full sampling | 8db9-c1c8-fd68 | N | N | N | 8 | 2018-05-22 | 10:00AM | GB | 0:8 | 2018-06-26 | Barnstable | 237 | All Results sent | NE, C, SE
ClintonPS | CLINTON | 2018-05-23 | Full sampling | 454c-ae3b-9b86 | N | N | N | 4 | 2018-02-16 | 9:00AM | LL | 3 :4 | 2018-04-14 | MWRA | 314 | All Results sent | Central | LL
Dracut | DRACUT | 2018-01-02 | Follow up | 1a3c-c76b-6dc8 | N | N | Y | 1 | none needed |  | RL |  |  |  |  | Advice given | Northeast |  | Helped with Tool
GraftonPS | GRAFTON | 2018-03-28 | Full sampling | 564b-9d1d-ba83 | N | N | N | 6 | 2017-12-07 | 10:00AM | LL | 6:6 | 2018-02-27 | RI Analytical | 387 | All Results sent | Central | LL
HaverhillComAct | HAVERHILL | 2018-06-14 | Full sampling | ccfc-01a5-1f2c | N | N | N | 3 | 2018-05-09 | 10:00AM | GB | 3:3 | 2018-05-22 | Granite | 59 | All Results sent | Northeast | GB
LeominsterPS | LEOMINSTER | 2018-01-29 | Full sampling | 185f-1c77-28c1 | N | N | N | 11 | 2017-11-06 | 10:00AM | GB | 9:11 | 2018-01-09 | Alpha Analytical | 216 | All results sent | Central | GB
Little Folks | EAST BOSTON | 2018-06-07 | Full sampling | a2ab-4c07-7ef5 | N | Y | N | 2 | 2018-04-27 | 10:00AM | BH | 2:2 | 2018-06-06 | MWRA | 30 | All Results sent | Northeast
LongmeadowPS | LONGMEADOW | 2018-04-30 |  | 86cc-b06e-fd11 | N | N | Y | 6 | [7 empty] | No response | Western |  | No response, but were done last year
LudlowPS | LUDLOW | 2018-06-26 | Full sampling | 2fa8-1f42-4e34 | N | N | N | 6 | 2018-02-22 | 09:30AM | MI | 6:6 | 2018-04-28 | Eurofins | 463 | All Results sent | Western | MI
LunenburgPS | LUNENBURG | 2018-06-04 | Full sampling | d17f-4f5d-9910 | N | N | N | 4 | 2018-05-11 | 9:00AM | GB | 4:4 | 2018-06-02 | Granite | 311 | All Results sent | Central
LynnfieldPS | LYNNFIELD | 2018-08-16 | Full sampling | c8a4-b8ab-6882 | N | Y | N | 4 | 2018-05-03 | 10:00AM | GB | 4:4 | 2018-05-26 | Granite | 420 | All Results sent | Northeast | GB
MansfieldPS | MANSFIELD | 2018-02-12 | Full sampling | 74c0-e2f6-5dce | N | N | N | 5 | 2017-11-16 | 10:00AM | GB | 5:5 | 2018-02-08 | Alpha Analytical | 504 | All results sent | Southeast | GB, TB
MasconometRSD | BOXFORD | 2018-06-18 | Full sampling | 2713-1fd5-c636 | Y | N | N | 1 | 2018-05-24 | 1:30PM | BH | 1:1 | 2018-06-16 | RI Analytical | 91 | All results sent | Northeast
MaynardPS | MAYNARD | 2018-05-16 | Full sampling | 48cf-a446-d8ca | N | N | N | 3 | 2018-05-21 | 9:30AM | LL | 0:3 |  | RI Analytical |  | IM completed | Central |  | Not responding to TAP
MillisPS | MILLIS | 2018-04-27 | Out of Program | 8e0f-afa3-a415 | N | N | N | 1 | Out of Program |  | RL |  | Out of Program |  |  | Out of Program | Central |  | They say they already do exactly the same on their own and will ask their lab to submit data to DEP
NarragansetRSD | BALDWINVILLE | 2018-05-04 | Full sampling | 2da6-9d78-7318 | N | N | N | 3 | [6 empty] | 0 | Ready to schedule IM | Central
NashValTSD | WESTFORD | 2017-11-20 | Full sampling | 9962-a138-74ba | N | N | N | 1 | 2017-10-02 | 9:00AM | GB | 1:1 | 2017-11-02 | RI Analytical | 81 | All results sent | Northeast | GB
NMRSD | PEPPERELL | 2018-04-30 |  | fe15-f441-f2cf | N | N | Y | 1 | [7 empty] | Waiting list | Central |  | This one school was out of program last year
North ReadingPS | NORTH READING | 2018-06-29 | Full sampling | 89ba-0b5c-7901 | N | N | N | 5 | 2018-05-02 | 10:00AM | GB | 5:5 | 2018-05-30 | Alpha Analytical | 385 | All Results sent | Northeast
NRSD | BOLTON | 2018-03-21 | Full sampling | d10e-83ca-eb31 | Y | N | N | 6 | 2017-12-11 | 10:00AM | GB | 6:6 | 2018-02-15 | RI Analytical | 566 | All results sent | Central | GB
NSWSD | NEW SALEM | 2018-04-20 | Full sampling | a822-7e6a-8e04 | Y | N | N | 1 | 2018-01-30 | 10:00AM | MI | 1:1 | 2018-03-02 | Granite | 56 | All Results sent | Western | MI
PittsfieldPS | PITTSFIELD | 2018-06-29 | Full sampling | f8f5-52a9-bad2 | N | N | N | 12 | 2018-05-03 | 10:00AM | MI | 11:12 | 2018-05-26 | Eurofins | 658 | All Results sent | Western | MI
PositiveRegard | HOLYOKE | 2018-06-26 | Full sampling | abca-e8e8-abf7 | N | N | N | 2 | 2018-05-10 | 9:30AM | MI | 2:2 | 2018-05-19 | Eurofins | 31 | All Results sent | Western | MI
RandolphPS | RANDOLPH | 2018-05-10 | Out of Program | c1c2-d0d6-d27c | N | N | N | 6 | Out of Program |  |  |  | Out of Program |  |  | No response | Southeast |  | No response
ReadingPS | READING | 2017-12-04 | Follow up | 56d8-2e54-5df8 | N | Y | N | 1 | none needed |  | RL |  |  |  | 0 | Advice given | Northeast
ReverePS | REVERE | 2017-12-04 | None | 4c3d-8fe9-1788 | N | Y | N | 4 | none needed |  |  |  |  | MWRA | 0 | They sampled with MWRA already | Northeast
SBRSD | SHEFFIELD | 2018-08-01 | Full sampling | c3ee-b69c-0b74 | N | N | N | 2 | 2018-05-03 | 10:00AM | MI | 2:2 | 2018-06-15 | Eurofins | 168 | All Results sent | Western
SEBRSD | SPENCER | 2018-06-22 | Full sampling | 1091-54f5-f19b | N | N | N | 4 | 2018-04-23 | 9:00AM | LL | 4:4 | 2018-05-15 | Alpha Analytical | 257 | All Results sent | Central | LL
SelfHelp | BROCKTON | 2018-08-13 | Full sampling | f4d5-ee2f-a606 | N | N | N | 3 | 2018-05-24 |  | GB | 3:3 | 2018-06-05 | RI Analytical | 117 | All Results sent | Southeast
Shutesbury ES | SHUTESBURY | 2018-06-20 | Full sampling | 9b2e-c929-f1ad | Y | N | N | 1 | 2018-05-29 | 9:00AM | JT | 1:1 | 2018-06-20 | Eurofins | 40 | All Results sent | Western
South Hadley PS | SOUTH HADLEY | 2018-06-18 | Full sampling | 5486-e4cc-0d8f | Y | Y | N | 4 | 2018-05-31 | 9:30AM | JT, RL | 4:4 | 2018-06-16 | MWRA | 263 | All Results sent | Western | JT, RL
SouthShoreCPS | NORWELL | 2018-06-04 | Full sampling | ceda-3e64-3a3c | N | N | N | 1 | 2018-02-12 | 01:00PM | TB | 1:1 | 2018-05-11 | Alpha Analytical | 26 | All Results sent | Southeast
Springfield | SPRINGFIELD | 2018-01-02 | Follow up | 20d2-d383-fc0f | N | N | Y | 52 | none needed |  | RL |  |  |  |  | Advice given | Western |  | Helped with Cu Exceedances
St Vincent's Home | FALL RIVER | 2018-04-27 |  | e185-c41e-c9a1 | N | N | N | 1 | [7 empty] | Waiting list | Northeast
StoughtonPS | STOUGHTON | 2018-03-21 | Full sampling | c322-b1d2-a016 | N | N | N | 8 | 2018-02-20 | 10:00AM | GB | 8:8 | 2018-02-28 | Alpha Analytical | 162 | All results sent | Southeast | GB
SudburyPS | SUDBURY | 2018-08-08 | Full sampling | 636d-df8c-c2e6 | N | N | N | 5 | 2018-05-21 | 9:30 | LL | 5:5 | 2018-05-31 | RI Analytical | 513 | All Results sent | Northeast | LL
TantasquaRSD | FISKDALE | 2018-08-16 | Full sampling | 0646-20fd-b0b2 | Y | N | N | 2 | 2018-05-25 | 9:00AM | GB | 2:2 | 2018-06-07 | RI Analytical | 134 | All Results sent | Central | TB
TEC-COOP | EAST WALPOLE | 2018-04-27 | Full sampling | 998e-32db-f396 | N | N | N | 1 | 2018-04-09 | 11:00AM | GB | 1:1 | 2018-04-27 | RI Analytical | 41 | All Results sent | Southeast | GB
TritonRSD | BYFIELD | 2018-04-20 | Full sampling | 51d3-99e5-3ff9 | N | N | N | 4 | 2017-11-15 | 09:00AM | GB | 5:5 | 2018-01-27 | Granite | 642 | All Results sent | Northeast | GB,TB
Tri-Town School Union | BOXFORD | 2018-06-22 | Full sampling | 2c25-1998-195a | Y/N | N | N | 6 | 2018-05-24 | 1:30PM | BH | 6:6 | 2018-06-19 | RI Analytical | 612 | All Results sent | Northeast
UMassAmherstCEEC | AMHERST | 2018-02-22 | Full sampling | c101-79a5-b3fb | N | N | N | 1 | 2017-10-19 | 11:00AM | RL | 1:1 | 2018-02-22 | Alpha Analytical | 7 | All results sent | Western | RL | Sampled by John Tobiason
WachusettRSD | JEFFERSON | 2018-02-12 | Full sampling | cfbc-de6f-1220 | N | N | N | 12 | 2017-12-18 | 9:00AM | GB | 12:12 | 2018-01-25 | Alpha Analytical | 1215 | All results sent | Central | GB
WalthamCCC | WALTHAM | 2018-04-27 | Out of Program | 7fd6-b19a-f6ef | N | Y | N | 1 | Out of Program |  |  |  | Out of Program |  |  | Out of Program | Northeast |  | Said she doesn't have enough students (21)
WestboroughPS | WESTBOROUGH | 2018-03-28 | Full sampling | dd95-03e7-6603 | N | N | Y | 1 | none needed |  | na | 1:1 | 2018-02-01 | Alpha Analytical | 52 | All results sent | Central |  | didn't get results, but they are posted on Tool
WestfordPS | WESTFORD | 2018-01-24 | Full sampling | 7496-806e-3952 | N | N | N | 10 | 2017-11-02 | 10:00AM | GB | 10:10 | 2018-01-13 | RI Analytical | 732 | All results sent | Northeast | GB
Weston PS | WESTON | 2018-08-24 |  | c1ee-1657-1b5f | N | Y | N | 5 | [7 empty] | Waiting list | Northeast
WeymouthPS | WEYMOUTH | 2018-04-11 | Out of Program | 378e-e109-83ca | N | N | N | 13 | Out of Program |  | GB |  | Out of Program |  |  | Out of Program | Southeast |  | Says they screened last year and are all set
Wilmington | WILMINGTON | 2018-01-02 | Follow up | f51d-0aac-243b | N | Y | Y | 8 | none needed |  | RL |  |  |  |  | Advice given | Northeast |  | Helped with Tool
WLPS | WILLIAMSTOWN/ LANESBOROUGH | 2017-12-20 | Full sampling | d552-6585-5c61 | N | N | N | 2 | 2017-11-27 | 10:00AM | MI | 2:2 | 2017-01-27 | Alpha Analytical | 223 | All results sent | Western | MI
WorcesterPS | WORCESTER | 2017-12-19 | Follow up | be6e-d2bf-4f12 | N | N | Y | 3 | none needed |  | RL |  |  |  |  | Advice given | Central |  | Helped with Tool and Lab Uploading of data

## Facilities
Admin Unit | Location | Date Record Updated | PWS ID | PWS | MWRA Lab? | ORG Code | Facility Name | Facilty Type | Year(s) Facility Built | Status | Sample Plan | Sample Date | # Sample Locations | # Samples | Sampling completed? | Results received? | Results sent? | total # samples in admin unit | Field CoC Uploaded to Tool | Additional Sample Locations Uploaded to Tool? | Any Pb > AL? (Y/N) | Any Cu > AL? (Y/N) | # FD(P) samples >= Pb AL | # flush samples >= Pb AL | # FD(P) samples >= Cu AL | # flush samples >= Cu AL | Not yet completed | Staff & Task | Time estimate to finish | DEP Region
BaystateACPS | SPRINGFIELD | 2018-07-02 | 1281000 | N | N | 35020405 | Baystate Academy Charter Public School | SCHOOL |  | A- all done | completed | 2018-03-31 | 13 | 26 | Y | Y | 2018-05-17 | 26 | Y |  | N | N | 0 | 0 | 0 | 0
BraintreePS | BRAINTREE | 2018-06-15 | 4040000 | N | N | 00400033 | Archie T Morrison Elementary School | SCHOOL |  | A- all done | completed | 2018-06-14 | 72 | 90 | Y | Y | 2018-07-24 |  | Y | Y | Y | N | 14 | 2 | 0 | 0
BraintreePS | BRAINTREE | 2018-06-15 | 4040000 | N | N | 00400505 | Braintree High School | SCHOOL |  | A- all done | completed | 2018-06-12 | 60 | 103 | Y | Y | 2018-07-24 |  | Y |  | Y | Y | 3 | 3 | 0 | 1
BraintreePS | BRAINTREE | 2018-06-15 | 4040000 | N | N | 00400050 | Donald Ross Elementary School | SCHOOL |  | A- all done | completed | 2018-06-14 | 38 | 59 | Y | Y | 2018-07-24 |  | Y |  | Y | N | 4 | 0 | 0 | 0
BraintreePS | BRAINTREE | 2018-06-15 | 4040000 | N | N | 00400305 | East Middle School | SCHOOL |  | A- all done | completed | 2018-06-13 | 19 | 28 | Y | Y | 2018-07-24 |  | Y |  | N | N | 0 | 0 | 0 | 0
BraintreePS | BRAINTREE | 2018-06-15 | 4040000 | N | N | 00400015 | Highlands Elementary School | SCHOOL |  | A- all done | completed | 2018-06-13 | 35 | 52 | Y | Y | 2018-07-24 |  | Y |  | N | N | 0 | 0 | 0 | 0
BraintreePS | BRAINTREE | 2018-06-15 | 4040000 | N | N | 00400005 | Hollis Elementary School | SCHOOL |  | A- all done | completed | 2018-06-13 | 25 | 47 | Y | Y | 2018-07-24 |  | Y |  | Y | N | 2 | 1 | 0 | 0
BraintreePS | BRAINTREE | 2018-06-21 | 4040000 | N | N | 00400025 | Liberty Elementary School | SCHOOL |  | A- all done | completed | 2018-06-20 | 45 | 63 | Y | Y | 2018-07-24 |  | Y |  | Y | N | 8 | 3 | 0 | 0
BraintreePS | BRAINTREE | 2018-06-21 | 4040000 | N | N | 00400020 | Mary E Flaherty Elementary School | SCHOOL |  | A- all done | completed | 2018-06-20 | 39 | 64 | Y | Y | 2018-07-24 |  | Y |  | Y | N | 1 | 0 | 0 | 0
BraintreePS | BRAINTREE | 2018-06-15 | 4040000 | N | N | 00400009 | Monatiquot Kindergarten Center | SCHOOL |  | A- all done | completed | 2018-06-12 | 41 | 59 | Y | Y | 2018-07-25 |  | Y |  | Y | N | 3 | 0 | 0 | 0
BraintreePS | BRAINTREE | 2018-06-15 | 4040000 | N | N | 00400310 | South Middle School | SCHOOL |  | A- all done | completed | 2018-06-13 | 16 | 28 | Y | Y | 2018-07-24 | 593 | Y |  | N | N | 0 | 0 | 0 | 0
BRRSD | BRIDGEWATER | 2018-08-24 | 4042000 | N | N | 06250320 | Bridgewater Middle School | SCHOOL |  | A- all done | completed | 2018-06-19 | 28 | 50 | Y | Y | 2018-08-22 |  | Y |  | Y | Y | 3 | 1 | 3 | 1
BRRSD | BRIDGEWATER | 2018-08-24 | 4042000 | N | N | 06250505 | Bridgewater-Raynham Regional High School | SCHOOL |  | A- all done | completed | 2018-06-21 | 32 | 55 | Y | Y | 2018-08-22 |  | Y |  | Y | Y | 2 | 0 | 5 | 1
BRRSD | BRIDGEWATER | 2018-07-26 | 4245000 | N | N | 06250050 | Laliberte Elementary School | SCHOOL |  | A- all done | completed | 2018-06-08 | 72 | 106 | Y | Y | 2018-07-26 |  | Y |  | Y | N | 1 | 0 | 0 | 0
BRRSD | BRIDGEWATER | 2018-07-26 | 4245000 | N | N | 06250020 | LB Merrill Elementary School | SCHOOL |  | A- all done | completed | 2018-06-08 | 54 | 79 | Y | Y | 2018-07-26 |  | Y |  | Y | N | 1 | 0 | 0 | 0
BRRSD | RAYNHAM | 2018-08-01 | 4245000 | N | N | 06250315 | Raynham Middle School | SCHOOL |  | A- all done | completed | 2018-06-07 | 112 | 166 | Y | Y | 2018-08-01 |  | Y |  | Y | Y | 7 | 1 | 2 | 0
BRRSD | BRIDGEWATER | 2018-08-24 | 4042000 | N | N | 06250300 | Williams Intermediate School | SCHOOL |  | A- all done | completed | 2018-06-20 | 26 | 43 | Y | Y | 2018-08-22 | 499 | Y |  | N | Y | 0 | 0 | 0 | 1
Children's Workshop | WESTBOROUGH | 2018-07-27 | 2328000 | N | N | 8030041 | The Childrens Workshop | EECF |  | A- all done | completed | 2018-06-27 | 10 | 19 | Y | Y | 2018-07-27 |  | Y |  | N | N | 0 | 0 | 0 | 0 |  |  |  | Central
Children's Workshop | WALTHAM | 2018-06-29 | 3308000 | N | Y | 290279 | The Children's Workshop | EECF |  | A- all done | completed | 2018-06-26 | 19 | 35 | Y | Y | 2018-07-18 |  | Y |  | N | N | 0 | 0 | 0 | 0 |  |  |  | Northeast
Children's Workshop | SOUTH DENNIS | 2018-06-29 | 4075000 | N | N | 2912198 | The Children's Workshop | EECF |  | A- all done | completed | 2018-06-28 | 10 | 18 | Y | Y | 2018-07-18 |  | Y |  | N | Y | 0 | 0 | 0 | 1 |  |  |  | Southeast
Children's Workshop | SEEKONK | 2018-06-29 | 4265000 | N | N | 212550 | The Children's Workshop | EECF |  | A- all done | completed | 2018-06-28 | 13 | 25 | Y | Y | 2018-07-18 |  | Y |  | N | N | 0 | 0 | 0 | 0 |  |  |  | Southeast
Children's Workshop | NORWOOD | 2018-07-27 | 4220000 | N | Y | 290388 | The Children's Workshop | EECF |  | A- all done | completed | 2018-06-26 | 23 | 36 | Y | Y | 2018-07-27 |  | Y |  | N | N | 0 | 0 | 0 | 0 |  |  |  | Southeast
Children's Workshop | NORTH ATTLEBORO | 2018-07-27 | 4211000 | N | N | 290187 | The Children's Workshop | EECF |  | A- all done | completed | 2018-06-27 | 20 | 31 | Y | Y | 2018-07-27 |  | Y |  | N | N | 0 | 0 | 0 | 0 |  |  |  | Southeast
Children's Workshop | WEST BRIDGEWATER | 2018-07-27 | 4322000 | N | N | 211741 | The Children's Workshop | EECF |  | A- all done | completed | 2018-06-28 | 25 | 43 | Y | Y | 2018-07-27 |  | Y |  | N | Y | 0 | 0 | 2 | 0 |  |  |  | Southeast
Children's Workshop | BOURNE | 2018-08-16 | 4036001 | N | N | 2911958 | The Children's Workshop | EECF |  | A- all done | completed | 2018-06-29 | 16 | 30 | Y | Y | 2018-08-16 | 237 |  |  | Y | N | 0 | 0 | 0 | 0 |  |  |  | Southeast
ClintonPS | CLINTON | 2018-07-11 | 2064000 | N | Y | 00640050 | Clinton Elementary School | SCHOOL | 2003 | A- all done | completed | 2018-04-14 | 140 | 214 | Y | Y | 2018-05-23 |  | Y |  | N | N | 0 | 0 | 0 | 0
ClintonPS | CLINTON | 2018-07-11 | 2064000 | N | Y | 00640305 | Clinton Middle School | SCHOOL | 1975 | A- all done | completed | 2018-04-14 | 42 | 41 | Y | Y | 2018-05-23 |  | Y |  | Y | N | 2 | 0 | 0 | 0
ClintonPS | CLINTON | 2018-07-11 | 2064000 | N | Y | 00640505 | Clinton Senior High School | SCHOOL | 1999 | A- all done | completed | 2018-04-24 | 37 | 59 | Y | Y | 2018-05-23 | 314 | Y |  | N | N | 0 | 0 | 0 | 0
GraftonPS | GRAFTON | 2018-03-28 | 2110000 | N | N | 01100505 | Grafton High School | SCHOOL | 2012 | A- all done | completed | 2018-03-07 | 46 | 73 | Y | Y | 2018-03-28 |  | Y |  | Y | Y | 1 | 0 | 4 | 8
GraftonPS | GRAFTON | 2018-03-21 | 2110000 | N | N | 01100305 | Grafton Middle School | SCHOOL | 1964+1995 | A- all done | completed | 2018-02-27 | 19 | 28 | Y | Y | 2018-03-21 |  | Y |  | Y | Y | 1 | 0 | 4 | 1
GraftonPS | GRAFTON | 2018-03-21 | 2110000 | N | N | 01100200 | Millbury Street Elementary School | SCHOOL | 2002 | A- all done | completed | 2018-02-28 | 95 | 137 | Y | Y | 2018-03-21 |  | Y |  | Y | N | 2 | 0 | 0 | 0
GraftonPS | GRAFTON | 2018-03-21 | 2110000 | N | N | 01100025 | North Grafton Elementary School | SCHOOL | 1955 | A- all done | completed | 2018-02-27 | 41 | 61 | Y | Y | 2018-03-21 |  | Y |  | Y | Y | 25 | 0 | 1 | 0
GraftonPS | GRAFTON | 2018-03-28 | 2110000 | N | N | 01100030 | North Street Elementary School | SCHOOL | 1969+1995 | A- all done | completed | 2018-03-02 | 17 | 20 | Y | Y | 2018-03-28 |  | Y |  | Y | Y | 1 | 0 | 6 | 2
GraftonPS | GRAFTON | 2018-03-28 | 2110001 | N | N | 01100005 | South Grafton Elementary School | SCHOOL | 1974 | A- all done | completed | 2018-03-02 | 44 | 68 | Y | Y | 2018-03-28 | 387 | Y |  | Y | N | 1 | 0 | 0 | 0
HaverhillComAct | NEWBURYPORT | 2018-06-15 | 3206000 | N | N | 290769 | Community Action Headstart at Newburyport | EECF |  | A- all done | completed | 2018-05-22 | 6 | 11 | Y | Y | 2018-06-14 | 59 | Y |  | N | N | 0 | 0 | 0 | 0
HaverhillComAct | HAVERHILL | 2018-06-15 | 3128000 | N | N | 200704 | Community Action Headstart Fox Center | EECF |  | A- all done | completed | 2018-05-22 | 20 | 36 | Y | Y | 2018-06-14 |  | Y |  | N | N | 0 | 0 | 0 | 0
HaverhillComAct | HAVERHILL | 2018-06-15 | 3128000 | N | N | 212295 | Community Action Headstart-Goldman Center | EECF |  | A- all done | completed | 2018-05-22 | 6 | 12 | Y | Y | 2018-06-14 |  | Y |  | N | N | 0 | 0 | 0 | 0
LeominsterPS | LEOMINSTER | 2018-02-01 | 2153000 | N | N | 01530003 | Bennett School | SCHOOL | 1878 | A- all done | completed | 2018-01-09 | 7 | 6 | Y | Y | 2018-01-23 |  | Y |  | Y | N | 1 | 0 | 0 | 0
LeominsterPS | LEOMINSTER | 2018-02-01 | 2153000 | N | N | 01530007 | Fall Brook Elementary Schhol | SCHOOL | 1966 | A- all done | completed | 2018-01-12 | 15 | 25 | Y | Y | 2018-01-29 |  | Y |  | N | Y | 0 | 0 | 1 | 0
LeominsterPS | LEOMINSTER | 2018-02-01 | 2153000 | N | N | 01530010 | Frances Drake School | SCHOOL | 1970 | A- all done | completed | 2018-01-11 | 9 | 18 | Y | Y | 2018-01-29 |  | Y |  | Y | N | 1 | 0 | 0 | 0
LeominsterPS | LEOMINSTER | 2018-02-01 | 2153000 | N | N | 01530025 | Johnny Appleseed School | SCHOOL | 1959 | A- all done | completed | 2018-01-11 | 11 | 21 | Y | Y | 2018-01-29 |  | Y | Y (2) | Y | N | 3 | 0 | 2 | 0
LeominsterPS | LEOMINSTER | 2018-02-01 | 2153000 | N | N | 01530505 | Leominster High School | SCHOOL | 1963 | A- all done | completed | 2018-01-09 | 32 | 61 | Y | Y | 2018-01-29 |  | Y |  | Y | Y | 3 | 0 | 3 | 2
LeominsterPS | LEOMINSTER | 2018-02-01 | 2153000 | N | N | 01530030 | Northwest School | SCHOOL | 1956 | A- all done | completed | 2018-01-10 | 11 | 19 | Y | Y | 2018-01-29 |  | Y |  | Y | N | 1 | 0 | 0 | 0
LeominsterPS | LEOMINSTER | 2018-02-01 | 2153000 | N | N | 01530040 | Priest Street | SCHOOL | 1894 | A- all done | completed | 2018-01-12 | 3 | 6 | Y | Y | 2018-01-29 |  | Y |  | N | N | 0 | 0 | 0 | 0
LeominsterPS | LEOMINSTER | 2018-02-01 | 2153000 | N | N | 01530045 | Samoset School | SCHOOL | 1995 | A- all done | completed | 2018-01-12 | 11 | 21 | Y | Y | 2018-01-29 |  | Y |  | Y | N | 1 | 0 | 0 | 0
LeominsterPS | LEOMINSTER | 2018-03-15 | 2153000 | N | N | 01530320 | Sky View Middle School | SCHOOL | 2003 | A- all done | completed | 2018-01-10 | 25 | 39 | Y | Y | 2018-01-29 | 216 | Y |  | N | N | 0 | 0 | 0 | 0 | Initial datafile errors; resent 3/8
Little Folks | EAST BOSTON | 2018-07-11 | 3035000 | N | Y | 200954 | Little Folks Community Day Care Center | EECF |  | A- all done | completed | 2018-06-06 | 11 | 22 | Y | Y | 2018-07-13 |  | Y |  | Y | N | 1 | 0 | 0 | 0 |  |  |  | Northeast
Little Folks | BOSTON | 2018-07-11 | 3035001 | N | Y | 390615 | Swift Water After School Program | EECF |  | A- all done | completed | 2018-06-06 | 4 | 8 | Y | Y | 2018-07-13 | 30 | Y |  | N | N | 0 | 0 | 0 | 0
LudlowPS | LUDLOW | 2018-07-11 | 1281000 | N | N | 01610020 | Chapin Street Elementary School | SCHOOL |  | A- all done | completed | 2018-05-12 | 49 | 76 | Y | Y | 2018-06-22 |  | Y |  | Y | Y | 2 | 1 | 2 | 1
LudlowPS | LUDLOW | 2018-06-22 | 1281000 | N | N | 01610010 | East Street Elementary School | SCHOOL | 1921+1959 | A- all done | completed | 2018-04-28 | 86 | 131 | Y | Y | 2018-06-22 |  | Y |  | Y | Y | 2 | 0 | 2 | 0
LudlowPS | LUDLOW | 2018-04-30 | 1281000 | N | N | 01610505 | Ludlow Senior High School | SCHOOL | 1962 | A- all done | completed | 2018-04-28 | 56 | 88 | Y | Y | 2018-07-13 |  | Y |  | Y | Y | 1 | 0 | 12 | 1
LudlowPS | LUDLOW | 2018-06-01 | 1281001 | N | N | 201306 | Parkside Early Learning Center | EECF |  | A- all done | completed | 2018-05-12 | 3 | 6 | Y | Y | 2018-07-13 |  | Y |  | N | Y | 0 | 0 | 1 | 1
LudlowPS | LUDLOW | 2018-06-01 | 1281000 | N | N | 01610305 | Paul R Baird Middle School | SCHOOL | 1973 | A- all done | completed | 2018-04-28 | 32 | 64 | Y | Y | 2018-07-13 |  | Y |  | N | Y | 0 | 0 | 2 | 0
LudlowPS | LUDLOW | 2018-07-11 | 1281000 | N | N | 01610023 | Veterans Park Elementary School | SCHOOL |  | A- all done | completed | 2018-05-12 | 60 | 98 | Y | Y | 2018-06-26 | 463 | Y |  | Y | Y | 4 | 1 | 1 | 1
LunenburgPS | LUNENBURG | 2018-07-11 | 2162000 | N | N | 01620505 | Lunenburg High School | SCHOOL |  | A- all done | completed | 2018-06-02 | 60 | 97 | Y | Y | 2018-07-13 |  | Y |  | N | N | 0 | 0 | 0 | 0
LunenburgPS | LUNENBURG | 2018-07-11 | 2162000 | N | N | 01620010 | Lunenburg Primary School | SCHOOL |  | A- all done | completed | 2018-06-02 | 67 | 97 | Y | Y | 2018-07-19 |  | Y |  | N | N | 0 | 0 | 0 | 0
LunenburgPS | LUNENBURG | 2018-07-11 | 2162000 | N | N | 01620015 | Thomas C Passios Elementary School | EECF |  | A- all done | completed | 2018-06-02 | 39 | 59 | Y | Y | 2018-07-19 |  | Y |  | Y | Y | 17 | 2 | 2 | 1
LunenburgPS | LUNENBURG | 2018-07-11 | 2162000 | N | N | 01620020 | Turkey Hill Middle School | SCHOOL |  | A- all done | completed | 2018-06-02 | 34 | 58 | Y | Y | 2018-07-19 | 311 | N |  | Y | Y | 10 | 1 | 0 | 1
LynnfieldPS | LYNNFIELD | 2018-06-20 | 3164004 | N | N | 01640010 | Huckleberry Hill Elementary School | SCHOOL |  | A- all done | completed | 2018-05-26 | 72 | 111 | Y | Y | 2018-06-20 |  | Y |  | Y | Y | 4 | 0 | 2 | 1
LynnfieldPS | LYNNFIELD | 2018-06-14 | 3164001 | N | N | 01640505 | Lynnfield High School | SCHOOL |  | A- all done | completed | 2018-05-26 | 31 | 54 | Y | Y | 2018-06-14 |  | Y |  | Y | N | 1 | 0 | 0 | 0
LynnfieldPS | LYNNFIELD | 2018-08-16 | 3164002 | N | N | 01640405 | Lynnfield Middle School | SCHOOL |  | A- all done | completed | 2018-05-26 | 84 | 133 | Y | Y | 2018-08-16 |  | Y |  | Y | N | 20 | 0 | 0 | 0
LynnfieldPS | LYNNFIELD | 2018-06-25 | 3164003 | N | N | 01640020 | Summer Street Elementary School | SCHOOL |  | A- all done | completed | 2018-05-26 | 72 | 122 | Y | Y | 2018-06-20 | 420 | Y |  | Y | N | 3 | 0 | 0 | 0
MansfieldPS | MANSFIELD | 2018-02-26 | 4167000 | N | N | 01670035 | Harold L Qualters Middle School | SCHOOL |  | A- all done | completed | 2018-02-10 | 38 | 63 | Y | Y | 2018-02-26 |  | Y |  | Y | Y | 8 | 2 | 14 | 9
MansfieldPS | MANSFIELD | 2018-02-26 | 4167000 | N | N | 01670014 | Jordan/Jackson Elementary School | SCHOOL |  | A- all done | completed | 2018-02-08 | 140 | 209 | Y | Y | 2018-03-01 |  | Y |  | Y | Y | 29 | 0 | 10 | 0 | Initial datafile errors; resent 3/8
MansfieldPS | MANSFIELD | 2018-02-26 | 4167000 | N | N | 01670505 | Mansfield High School | SCHOOL |  | A- all done | completed | 2018-02-10 | 41 | 58 | Y | Y | 2018-02-26 |  | Y |  | Y | Y | 9 | 0 | 5 | 3
MansfieldPS | MANSFIELD | 2017-10-24 | 4167000 | N | N | 01670007 | Robinson Elementary School | SCHOOL |  | A- all done | completed | 2018-02-10 | 96 | 164 | Y | Y | 2018-03-01 |  | Y |  | Y | Y | 39 | 1 | 20 | 21 | Initial datafile errors; resent 3/8
MansfieldPS | MANSFIELD | 2018-02-26 | 4167000 | N | N | 01670003 | Roland Green Pre-School | SCHOOL |  | A- all done | completed | 2018-02-10 | 5 | 10 | Y | Y | 2018-02-26 | 504 | Y |  | N | N | 0 | 0 | 0 | 0
MasconometRSD | BOXFORD | 2018-07-27 | 3298000 | Y | N | 07050000 | Masconomet Regional High & Middle School | SCHOOL |  | A- all done | completed | 2018-06-16 | 58 | 91 | Y | Y | 2018-07-27 | 91 | Y |  | Y | Y | 2 | 0 | 4 | 0
NashValTSD | WESTFORD | 2018-01-10 | 3330000 | N | N | 08520605 | Nashoba Valley Technical High School | SCHOOL |  | A- all done | completed | 2017-11-02 | 43 | 81 | Y | Y | 2017-11-28 | 81 | Y | N | Y | Y | 2 | 0 | 1 | 0
North ReadingPS | NORTH READING | 2018-07-11 | 3213000 | N | N | 02170003 | E Ethel Little Elementary School | SCHOOL |  | A- all done | completed | 2018-06-01 | 39 | 75 | Y | Y | 2018-06-22 |  | Y |  | Y | N | 1 | 0 | 0 | 0
North ReadingPS | NORTH READING | 2018-07-11 | 3213000 | N | N | 02170010 | J Turner Hood Elementary School | SCHOOL |  | A- all done | completed | 2018-05-31 | 66 | 86 | Y | Y | 2018-06-26 |  | Y |  | Y | Y | 3 | 0 | 1 | 0
North ReadingPS | NORTH READING | 2018-07-11 | 3213000 | N | N | 02170005 | L D Batchelder Elementary School | SCHOOL |  | A- all done | completed | 2018-06-01 | 62 | 108 | Y | Y | 2018-06-26 |  | Y |  | Y | Y | 1 | 1 | 2 | 0
North ReadingPS | NORTH READING | 2018-07-11 | 3213000 | N | N | 02170505 | North Reading High School | SCHOOL |  | A- all done | completed | 2018-05-30 | 46 | 72 | Y | Y | 2018-06-29 |  | Y |  | N | Y | 0 | 0 | 1 | 0
North ReadingPS | NORTH READING | 2018-07-11 | 3213000 | N | N | 02170305 | North Reading Middle School | SCHOOL |  | A- all done | completed | 2018-05-30 | 27 | 44 | Y | Y | 2018-06-22 | 385 | Y |  | N | N | 0 | 0 | 0 | 0
NRSD | STOW | 2017-10-26 | 2034028 | Y | N | 07250020 | Center School | SCHOOL |  | A- all done | completed | 2018-02-14 | 101 | 136 | Y | Y | 2018-03-16 |  | Y |  | N | N | 0 | 0 | 0 | 0
NRSD | BOLTON | 2017-10-26 | 2034024 | Y | N | 07250025 | Florence Sawyer School | SCHOOL |  | A- all done | completed | 2018-02-16 | 75 | 139 | Y | Y | 2018-03-21 |  | Y |  | Y | N | 4 | 0 | 0 | 0
NRSD | STOW | 2017-10-26 | 2034025 | Y | N | 07250310 | Hale Middle School | SCHOOL |  | A- all done | completed | 2018-02-17 | 29 | 49 | Y | Y | 2018-03-16 |  | Y |  | Y | N | 3 | 1 | 0 | 0
NRSD | LANCASTER | 2018-02-01 | 2034029 | Y | N | 07250305 | Luther Burbank Middle School | SCHOOL |  | A- all done | completed | 2018-02-15 | 20 | 36 | Y | Y | 2018-03-16 |  | Y |  | Y | Y | 3 | 2 | 1 | 0
NRSD | LANCASTER | 2018-03-16 | 2034026 | Y | N | 07250010 | Mary Rowlandson Elementary School | SCHOOL |  | A- all done | completed | 2018-02-15 | 81 | 128 | Y | Y | 2018-03-16 |  | Y |  | Y | N | 2 | 0 | 0 | 0
NRSD | BOLTON | 2018-03-21 | 2034027 | Y | N | 07250505 | Nashoba Regional High School | SCHOOL |  | A- all done | completed | 2018-02-17 | 48 | 78 | Y | Y | 2018-03-16 | 566 | Y |  | N | N | 0 | 0 | 0 | 0
NSWSD | NEW SALEM | 2018-04-20 | 1204001 | Y | N | 07280015 | Swift River School | SCHOOL | 1976+1987 | A- all done | completed | 2018-03-02 | 35 | 56 | Y | Y | 2018-04-20 | 56 | Y |  | N | N | 0 | 0 | 0 | 0
PittsfieldPS | PITTSFIELD | 2018-06-07 | 1236000 | N | N | 02360010 | Allendale Elementary School | SCHOOL | 1951+1999 | A- all done | completed | 2018-06-02 | 42 | 69 | Y | Y | 2018-07-18 |  | Y |  | Y | N | 0 | 1 | 0 | 0
PittsfieldPS | PITTSFIELD | 2018-06-29 | 1236000 | N | N | 02360065 | Crosby Elementary School | SCHOOL | 1962 | A- all done | completed | 2018-05-26 | 23 | 46 | Y | Y | 2018-06-29 |  | Y |  | Y | N | 2 | 0 | 0 | 0
PittsfieldPS | PITTSFIELD | 2018-06-07 | 1236000 | N | N | 02360035 | Egremont Elementary School | SCHOOL | 1951+1999 | A- all done | completed | 2018-06-02 | 53 | 84 | Y | Y | 2018-07-18 |  | Y |  | Y | N | 5 | 0 | 0 | 0
PittsfieldPS | PITTSFIELD | 2018-06-29 | 1236000 | N | N | 02360305 | John T Reid Middle School | SCHOOL | 1953+2000 | A- all done | completed | 2018-05-26 | 17 | 34 | Y | Y | 2018-06-29 |  | Y |  | N | N | 0 | 0 | 0 | 0
PittsfieldPS | PITTSFIELD | 2018-06-07 | 1236000 | N | N | 02360055 | Morningside Community School | SCHOOL | 1975 | A- all done | completed | 2018-06-02 | 44 | 78 | Y | Y | 2018-07-18 |  | Y |  | Y | N | 1 | 0 | 0 | 0
PittsfieldPS | PITTSFIELD | 2018-06-29 | 1236000 | N | N | 02360505 | Pittsfield High School | SCHOOL | 1931+1975 | A- all done | completed | 2018-05-26 | 17 | 34 | Y | Y | 2018-06-29 |  | Y |  | Y | Y | 2 | 0 | 0 | 1
PittsfieldPS | PITTSFIELD | 2018-06-07 | 1236000 | N | N | 02360045 | Robert T. Capeless Elementary School | SCHOOL | 1951+2001 | A- all done | completed | 2018-06-02 | 46 | 65 | Y | Y | 2018-07-18 |  | Y |  | N | N | 0 | 0 | 0 | 0
PittsfieldPS | PITTSFIELD | 2018-06-29 | 1236000 | N | N | 02360105 | Silvio O Conte Community School | SCHOOL | 1974 | A- all done | completed | 2018-05-26 | 40 | 74 | Y | Y | 2018-06-29 |  | Y |  | Y | N | 3 | 0 | 0 | 0
PittsfieldPS | PITTSFIELD | 2018-06-26 | 1236000 | N | N | 02360090 | Stearns Elementary School | SCHOOL | 1961+2001 | A- all done | completed | 2018-05-26 | 39 | 62 | Y | Y | 2018-06-26 |  | Y |  | N | Y | 0 | 0 | 1 | 0
PittsfieldPS | PITTSFIELD | 2018-06-29 | 1236000 | N | N | 02360310 | Theodore Herberg Middle School | SCHOOL | 1953+2000 | A- all done | completed | 2018-05-26 | 15 | 28 | Y | Y | 2018-06-29 |  | Y |  | N | N | 0 | 0 | 0 | 0
PittsfieldPS | PITTSFIELD | 2018-06-07 | 1236000 | N | N | 02360100 | Williams Elementary School | SCHOOL | 1957+1960+1962+1971+2001 | A- all done | completed | 2018-06-02 | 54 | 84 | Y | Y | 2018-07-19 | 658 | Y |  | N | N | 0 | 0 | 0 | 0
PositiveRegard | HOLYOKE | 2018-07-11 | 1137000 | N | N | 01370845 | Center School | SCHOOL |  | A- all done | completed | 2018-05-19 | 9 | 17 | Y | Y | 2018-06-26 |  | Y |  | Y | Y | 1 | 1 | 0 | 0
PositiveRegard | HOLYOKE | 2018-07-11 | 1137000 | N | N | 01370887 | Springdale Education Center | SCHOOL |  | A- all done | completed | 2018-05-19 | 7 | 14 | Y | Y | 2018-06-26 | 31 | Y |  | Y | N | 1 | 0 | 0 | 0
SBRSD | SHEFFIELD | 2018-08-01 | 1267000 | N | N | 07650505 | Mt Everett Regional School | SCHOOL |  | A- all done | completed | 2018-06-15 | 80 | 130 | Y | Y | 2018-08-01 |  | Y |  | N | N | 0 | 0 | 0 | 0
SBRSD | SHEFFIELD | 2018-08-01 | 1267000 | N | N | 07650035 | Undermountain Elementary School | SCHOOL |  | A- all done | completed | 2018-06-15 | 20 | 38 | Y | Y | 2018-08-01 | 168 | Y |  | N | N | 0 | 0 | 0 | 0
SEBRSD | SPENCER | 2018-06-08 | 2280000 | N | N | 07670505 | David Prouty High School | SCHOOL |  | A- all done | completed | 2018-05-21 | 14 | 21 | Y | Y | 2018-06-08 |  | Y |  | N | Y | 0 | 0 | 1 | 0
SEBRSD | SPENCER | 2018-06-22 | 2280000 | N | N | 07670008 | East Brookfield Elementary School | SCHOOL |  | A- all done | completed | 2018-05-24 | 52 | 84 | Y | Y | 2018-06-22 |  | Y |  | N | N | 0 | 0 | 0 | 0
SEBRSD | SPENCER | 2018-06-08 | 2280000 | N | N | 07670415 | Knox Trail Middle School | SCHOOL |  | A- all done | completed | 2018-05-23 | 18 | 34 | Y | Y | 2018-06-08 |  | Y |  | N | N | 0 | 0 | 0 | 0
SEBRSD | SPENCER | 2018-06-08 | 2280000 | N | N | 07670040 | Wire Village Elementary School | SCHOOL |  | A- all done | completed | 2018-05-15 | 93 | 118 | Y | Y | 2018-06-08 | 257 | Y |  | Y | N | 5 | 0 | 0 | 0
SelfHelp | NORTON | 2018-08-13 | 290181 | N | N | 290181 | Self Help Inc., Head Start | EECF |  | A- all done | completed | 2018-06-06 | 10 | 17 | Y | Y | 2018-08-13 |  | Y |  | Y | N | 1 | 0 | 0 | 0
SelfHelp | WHITMAN | 2018-08-13 | 290161 | N | N | 290161 | Self Help Inc., Head Start | EECF |  | A- all done | completed | 2018-06-06 | 8 | 15 | Y | Y | 2018-08-13 | 117 | Y |  | N | N | 0 | 0 | 0 | 0
SelfHelp | BROCKTON | 2018-07-02 | 4044000 | Y | N | 2911649 | Ulysses G Shelton Headstart Center | EECF |  | A- all done | completed | 2018-06-05 | 56 | 85 | Y | Y | 2018-07-02 |  | Y |  | N | N | 0 | 0 | 0 | 0
Shutesbury ES | SHUTESBURY | 2018-08-01 | 1272002 | Y | N | 02720005 | Shutesbury Elementary School | SCHOOL |  | A- all done | completed | 2018-06-20 | 20 | 40 | Y | Y | 2018-08-01 | 40 | Y |  | Y | N | 2 | 0 | 0 | 0
South Hadley PS | SOUTH HADLEY | 2018-08-03 | 1275001 | N | Y | 02780305 | Michael E Smith Middle School | SCHOOL | 1961+2000 | A- all done | completed | 2018-06-16 | 24 | 30 | Y | Y | 2018-08-03 |  | Y |  | Y | N | 1 | 0 | 0 | 0
South Hadley PS | SOUTH HADLEY | 2018-08-03 | 1275001 | N | Y | 02780020 | Mosier Elementary School | SCHOOL | 1969 | A- all done | completed | 2018-06-16 | 56 | 89 | Y | Y | 2018-08-03 |  | Y |  | Y | N | 2 | 0 | 0 | 0
South Hadley PS | SOUTH HADLEY | 2018-08-03 | 1275000 | N | Y | 02780015 | Plains Elementary School | SCHOOL | 2015 | A- all done | completed | 2018-06-16 | 62 | 97 | Y | Y | 2018-08-03 |  | Y |  | N | N | 0 | 0 | 0 | 0
South Hadley PS | SOUTH HADLEY | 2018-08-03 | 1275000 | N | Y | 02780505 | South Hadley High School | SCHOOL | 1955+2001 | A- all done | completed | 2018-06-18 | 26 | 47 | Y | Y | 2018-08-03 | 263 | Y |  | Y | Y | 1 | 2 | 2 | 3
SouthShoreCPS | NORWELL | 2018-06-04 | 4219000 | N | N | 04880550 | South Shore Charter Public School | SCHOOL |  | A- all done | completed | 2018-05-11 | 17 | 26 | Y | Y | 2018-06-04 | 26 | Y |  | N | Y | 0 | 0 | 1 | 0
StoughtonPS | STOUGHTON | 2017-10-24 | 4285000 | N | N | 02850012 | Edwin A Jones Early Childhood Center | SCHOOL | 1930+1954 | A- all done | completed | 2018-02-28 | 4 | 8 | Y | Y | 2018-03-21 |  | Y |  | Y | Y | 1 | 1 | 3 | 0
StoughtonPS | STOUGHTON | 2017-10-24 | 4285000 | N | N | 02850010 | Helen H Hansen Elementary School | SCHOOL |  | A- all done | completed | 2018-02-28 | 10 | 16 | Y | Y | 2018-03-21 |  | Y |  | N | Y | 0 | 0 | 1 | 0
StoughtonPS | STOUGHTON | 2018-03-28 | 4285000 | N | N | 02850025 | Joseph H Gibbons School | SCHOOL |  | A- all done | completed | 2018-03-01 | 10 | 19 | Y | Y | 2018-03-21 |  | Y |  | N | N | 0 | 0 | 0 | 0
StoughtonPS | STOUGHTON | 2018-02-14 | 4285000 | N | N | 02850014 | Joseph R Dawe Elementary School | SCHOOL | 1969 | A- all done | completed | 2018-03-01 | 10 | 19 | Y | Y | 2018-03-21 |  | Y |  | Y | Y | 2 | 1 | 4 | 0
StoughtonPS | STOUGHTON | 2018-03-21 | 4285000 | N | N | 02850405 | Robert G O'Donnell Middle School | SCHOOL |  | A- all done | completed | 2018-02-28 | 14 | 26 | Y | Y | 2018-03-21 |  | Y |  | N | N | 0 | 0 | 0 | 0
StoughtonPS | STOUGHTON | 2018-03-21 | 4285000 | N | N | 02850015 | South Elementary School | SCHOOL | 1958+1967 | A- all done | completed | 2018-03-01 | 8 | 16 | Y | Y | 2018-03-21 |  | Y |  | Y | Y | 2 | 0 | 3 | 3
StoughtonPS | STOUGHTON | 2018-03-21 | 4285000 | N | N | 02850505 | Stoughton High School | SCHOOL |  | A- all done | completed | 2018-02-28 | 20 | 40 | Y | Y | 2018-03-21 |  | Y |  | Y | Y | 9 | 1 | 3 | 3
StoughtonPS | STOUGHTON | 2018-03-21 | 4285000 | N | N | 02850020 | West Elementary School | SCHOOL |  | A- all done | completed | 2018-03-01 | 10 | 18 | Y | Y | 2018-03-21 | 162 | Y |  | N | N | 0 | 0 | 0 | 0
SudburyPS | SUDBURY | 2018-07-11 | 3288000 | N | N | 02880305 | Ephraim Curtis Middle School | SCHOOL |  | A- all done | completed | 2018-06-16 | 72 | 92 | Y | Y | 2018-07-13 |  | Y |  | N | N | 0 | 0 | 0 | 0
SudburyPS | SUDBURY | 2018-08-08 | 3288000 | N | N | 02880025 | General John Nixon Elementary School | SCHOOL |  | A- all done | completed | 2018-05-31 | 59 | 92 | Y | Y | 2018-08-07 |  | Y |  | Y | N | 5 | 0 | 0 | 0
SudburyPS | SUDBURY | 2018-07-11 | 3288000 | N | N | 02880015 | Israel Loring Elementary School | SCHOOL |  | A- all done | completed | 2018-06-16 | 81 | 126 | Y | Y | 2018-07-13 |  | Y |  | N | N | 0 | 0 | 0 | 0
SudburyPS | SUDBURY | 2018-07-02 | 3288000 | N | N | 02880010 | Josiah Haynes Elementary School | SCHOOL |  | A- all done | completed | 2018-06-09 | 61 | 96 | Y | Y | 2018-07-02 |  | Y |  | Y | N | 1 | 0 | 0 | 0
SudburyPS | SUDBURY | 2018-07-26 | 3288000 | N | N | 02880030 | Peter Noyes Elementary School | SCHOOL |  | A- all done | completed | 2018-06-23 | 75 | 107 | Y | Y | 2018-07-26 | 513 | Y |  | Y | Y | 6 | 1 | 0 | 0
TantasquaRSD | BRIMFIELD | 2018-08-13 | 1043014 | Y | N | 00430005 | Brimfield Elementary School | SCHOOL |  | A- all done | completed | 2018-06-07 | 59 | 92 | Y | Y | 2018-08-13 |  | Y |  | Y | N | 1 | 0 | 0 | 0
TantasquaRSD | HOLLAND | 2018-08-16 | 1135003 | Y | N | 01350005 | Holland Elementary School | SCHOOL |  | A- all done | completed | 2018-06-07 | 23 | 42 | Y | Y | 2018-08-16 | 134 | Y |  | N | N | 0 | 0 | 0 | 0
TEC-COOP | EAST WALPOLE | 2018-04-27 | 4307000 | N | N | 39020900 | Academy Commonwealth Virtual School | SCHOOL |  | A- all done | completed | 2018-04-27 | 22 | 41 | Y | Y | 2018-07-13 | 41 | Y |  | N | Y | 0 | 0 | 1 | 0 | ORG Code should be 05760000, according to Dan Shovak of The Education Cooperative
TritonRSD | NEWBURY | 2017-09-12 | 3205001 | N | N | 07730020 | Newbury Elementary School | SCHOOL |  | A- all done | completed | 2018-01-27 | 124 | 178 | Y | Y | 2018-03-16 |  | Y |  | Y | Y | 5 | 1 | 1 | 0
TritonRSD | ROWLEY | 2017-09-12 | 3254000 | N | N | 07730025 | Pine Grove School | SCHOOL |  | A- all done | completed | 2018-01-27 | 95 | 161 | Y | Y | 2018-02-15 |  | Y | Y(2) | Y | Y | 11 | 1 | 2 | 1
TritonRSD | SALISBURY | 2018-04-20 | 3259000 | N | N | 07730015 | Salisbury Elementary School | SCHOOL |  | A- all done | completed | 2018-01-27 | 121 | 176 | Y | Y | 2018-04-20 |  | Y |  | Y | Y | 5 | 0 | 61 | 0
TritonRSD | BYFIELD | 2017-12-13 | 3205001 | N | N | 07730505 | Triton Regional High School | SCHOOL |  | A- all done | completed | 2018-01-27 | 42 | 79 | Y | Y | 2018-02-15 |  | Y |  | Y | Y | 4 | 0 | 0 | 1 | Middle school has separate facility code: 07730405
TritonRSD | BYFIELD | 2018-03-16 | 3205001 | N | N | 07730405 | Triton Regional Middle School | SCHOOL |  | A- all done | completed | 2018-01-27 | 25 | 48 | Y | Y | 2018-02-06 | 642 | Y | Y (1) | Y | N | 3 | 0 | 0 | 0
Tri-Town School Union | MIDDLETON | 2018-07-26 | 3184000 | N | N | 01840003 | Fuller Meadow Elementary School | SCHOOL |  | A- all done | completed | 2018-06-22 | 43 | 80 | Y | Y | 2018-07-26 |  | Y |  | Y | Y | 5 | 5 | 1 | 1
Tri-Town School Union | BOXFORD | 2018-07-26 | 3038009 | Y | N | 00380005 | Harry Lee Cole Elementary School | SCHOOL |  | A- all done | completed | 2018-06-21 | 76 | 111 | Y | Y | 2018-07-26 |  | Y |  | Y | N | 3 | 0 | 0 | 0
Tri-Town School Union | MIDDLETON | 2018-07-26 | 3184000 | N | N | 01840005 | Howe-Manning Elementary School | SCHOOL |  | A- all done | completed | 2018-06-22 | 62 | 111 | Y | Y | 2018-07-26 |  | Y |  | N | N | 0 | 0 | 0 | 0
Tri-Town School Union | TOPSFIELD | 2018-07-26 | 3298000 | N | N | 02980005 | Proctor Elementary School | SCHOOL |  | A- all done | completed | 2018-06-19 | 64 | 103 | Y | Y | 2018-07-26 |  | Y |  | Y | N | 2 | 0 | 0 | 0
Tri-Town School Union | BOXFORD | 2018-07-26 | 3038008 | Y | N | 00380013 | Spofford Pond Elementary School | SCHOOL |  | A- all done | completed | 2018-06-21 | 74 | 107 | Y | Y | 2018-07-26 |  | Y |  | Y | N | 10 | 0 | 0 | 0
Tri-Town School Union | TOPSFIELD | 2018-07-26 | 3298000 | N | N | 02980010 | Steward Elementary School | SCHOOL |  | A- all done | completed | 2018-06-19 | 67 | 100 | Y | Y | 2018-07-26 | 612 | Y |  | N | N | 0 | 0 | 0 | 0
UMassAmherstCEEC | AMHERST | 2018-02-15 | 1008000 | N | N | 290857 | Center for Early Education and Care - UMass/Amherst | EECF |  | A- all done | completed | 2018-02-22 | 4 | 7 | Y | Y | 2018-03-01 | 7 | Y |  | N | N | 0 | 0 | 0 | 0
WachusettRSD | RUTLAND | 2018-03-15 | 2257000 | N | N | 07750310 | Central Tree Middle School | SCHOOL |  | A- all done | completed | 2018-02-01 | 52 | 79 | Y | Y | 2018-03-12 |  | Y |  | Y | Y | 7 | 0 | 1 | 0
WachusettRSD | STERLING | 2018-02-15 | 2282000 | N | N | 07750315 | Chocksett Middle School | SCHOOL |  | A- all done | completed | 2018-01-31 | 43 | 76 | Y | Y | 2018-03-12 |  | Y |  | Y | Y | 16 | 2 | 1 | 1
WachusettRSD | HOLDEN | 2018-02-06 | 2134000 | N | N | 07750018 | Davis Hill Elementary School | SCHOOL |  | A- all done | completed | 2018-02-06 | 84 | 133 | Y | Y | 2018-03-01 |  | Y | Y (4) | Y | Y | 7 | 0 | 14 | 2 | Initial datafile errors; resent 3/8
WachusettRSD | HOLDEN | 2018-03-01 | 2134000 | N | N | 07750020 | Dawson Elementary School | SCHOOL |  | A- all done | completed | 2018-02-02 | 69 | 104 | Y | Y | 2018-02-15 |  | Y |  | Y | N | 3 | 0 | 0 | 0
WachusettRSD | JEFFERSON | 2018-03-15 | 2134000 | N | N | 07750001 | Early Childhood Center | EECF |  | A- all done | completed | 2018-02-01 | 18 | 29 | Y | Y | 2018-02-15 |  | Y |  | Y | Y | 5 | 0 | 5 | 1
WachusettRSD | RUTLAND | 2018-03-15 | 2257000 | N | N | 07750060 | Glenwood Elementary School | SCHOOL |  | A- all done | completed | 2018-01-26 | 90 | 137 | Y | Y | 2018-03-09 |  | Y | Y (2) | Y | Y | 1 | 0 | 5 | 1
WachusettRSD | STERLING | 2018-03-15 | 2282000 | N | N | 07750027 | Houghton Elementary School | SCHOOL |  | A- all done | completed | 2018-01-31 | 55 | 106 | Y | Y | 2018-03-09 |  | Y |  | Y | Y | 9 | 1 | 0 | 1
WachusettRSD | JEFFERSON | 2018-03-15 | 2134000 | N | N | 07750032 | Leroy E Mayo Elementary School | SCHOOL |  | A- all done | completed | 2018-02-07 | 77 | 116 | Y | Y | 2018-03-01 |  | Y |  | Y | Y | 7 | 0 | 5 | 1 | Initial datafile errors; resent 3/8
WachusettRSD | HOLDEN | 2018-02-14 | 2134000 | N | N | 07750305 | Mountview Middle School | SCHOOL |  | A- all done | completed | 2018-02-03 | 54 | 85 | Y | Y | 2018-03-01 |  | Y | Y (1) | Y | N | 1 | 0 | 0 | 0 | Initial datafile errors; resent 3/8
WachusettRSD | RUTLAND | 2018-03-15 | 2257000 | N | N | 07750005 | Naquag Elementary School | SCHOOL |  | A- all done | completed | 2018-01-25 | 72 | 106 | Y | Y | 2018-02-15 |  | Y |  | Y | Y | 4 | 0 | 2 | 0
WachusettRSD | PAXTON | 2018-03-15 | 2228000 | N | N | 07750040 | Paxton Center School | SCHOOL |  | A- all done | completed | 2018-01-30 | 66 | 103 | Y | Y | 2018-03-09 |  | Y | Y (1) | N | Y | 0 | 0 | 2 | 0
WachusettRSD | HOLDEN | 2018-03-15 | 2134000 | N | N | 07750505 | Wachusett Regional High School | SCHOOL |  | A- all done | completed | 2018-02-03 | 84 | 141 | Y | Y | 2018-03-01 | 1215 | Y | Y (2) | Y | Y | 1 | 0 | 40 | 26 | Initial datafile errors; resent 3/8
WestboroughPS | WESTBOROUGH | 2018-02-15 | 2328000 | N | N | 03210305 | Sarah W Gibbons Middle School | SCHOOL |  | A- all done | completed | 2018-02-01 | 26 | 52 | Y | Y | 2018-03-28 | 52 | Y |  | N | N | 0 | 0 | 0 | 0
WestfordPS | WESTFORD | 2018-03-15 | 3330000 | N | N | 03260004 | Abbot Elementary School | SCHOOL |  | A- all done | completed | 2018-01-23 | 17 | 32 | Y | Y | 2018-03-01 |  | Y | Y (1) | Y | N | 3 | 0 | 0 | 0
WestfordPS | WESTFORD | 2018-03-15 | 3330000 | N | N | 03260310 | Blanchard Middle School | SCHOOL |  | A- all done | completed | 2018-01-23 | 23 | 35 | Y | Y | 2018-03-01 |  | Y |  | N | Y | 0 | 0 | 1 | 0
WestfordPS | WESTFORD | 2018-03-23 | 3330000 | N | N | 03260025 | Col. John Robinson School | SCHOOL |  | A- all done | completed | 2018-01-24 | 53 | 74 | Y | Y | 2018-03-01 |  | Y |  | Y | N | 6 | 0 | 0 | 0
WestfordPS | WESTFORD | 2018-03-28 | 3330000 | N | N | 03260045 | John A Crisafulli Elementary School | SCHOOL |  | A- all done | completed | 2018-01-20 | 72 | 113 | Y | Y | 2018-03-13 |  | Y |  | Y | N | 0 | 1 | 0 | 0
WestfordPS | WESTFORD | 2018-03-01 | 3330000 | N | N | 03260013 | Millennium Elementary School | SCHOOL |  | A- all done | completed | 2018-01-23 | 13 | 21 | Y | Y | 2018-03-01 |  | Y |  | Y | N | 1 | 0 | 0 | 0
WestfordPS | WESTFORD | 2018-03-01 | 3330000 | N | N | 03260015 | Nabnasset Elementary School | SCHOOL |  | A- all done | completed | 2018-01-20 | 66 | 104 | Y | Y | 2018-03-01 |  | Y |  | Y | Y | 8 | 0 | 1 | 0 | Initial datafile errors; resent 3/8
WestfordPS | WESTFORD | 2018-03-01 | 3330000 | N | N | 03260007 | Norman E Day Elementary School | SCHOOL |  | A- all done | completed | 2018-01-24 | 30 | 54 | Y | Y | 2018-03-01 |  | Y | Y (1) | Y | N | 2 | 0 | 0 | 0
WestfordPS | WESTFORD | 2018-03-15 | 3330000 | N | N | 03260055 | Rita E Miller Elementary School | SCHOOL |  | A- all done | completed | 2018-01-19 | 88 | 142 | Y | Y | 2018-03-01 |  | Y |  | Y | Y | 3 | 0 | 1 | 0 | Initial datafile errors; resent 3/8
WestfordPS | WESTFORD | 2018-03-01 | 3330000 | N | N | 03260330 | Stony Brook Middle School | SCHOOL |  | A- all done | completed | 2018-01-13 | 34 | 55 | Y | Y | 2018-02-08 |  | Y |  | N | N | 0 | 0 | 0 | 0
WestfordPS | WESTFORD | 2018-03-15 | 3330000 | N | N | 03260505 | Westford Academy | SCHOOL |  | A- all done | completed | 2018-01-13 | 62 | 102 | Y | Y | 2018-02-08 | 732 | Y |  | Y | N | 1 | 0 | 0 | 0
WLPS | LANESBOROUGH | 2018-01-30 | 1148000 | N | N | 01480005 | Lanesborough Elementary School | SCHOOL | 2001 | A- all done | completed | 2018-01-27 | 47 | 77 | Y | Y | 2018-02-15 |  | Y |  | N | N | 0 | 0 | 0 | 0
WLPS | WILLIAMSTOWN | 2018-01-28 | 1341000 | N | N | 03410010 | Williamstown Elementary School | SCHOOL | 2002 | A- all done | completed | 2018-02-17 | 91 | 146 | Y | Y | 2018-03-02 | 223 | Y |  | N | N | 0 | 0 | 0 | 0
MaynardPS | MAYNARD | 2018-05-22 | 2174000 | N | N | 01740305 | Fowler School | SCHOOL |  | F- IM Completed
MaynardPS | MAYNARD | 2018-05-22 | 2174000 | N | N | 01740010 | Green Meadow | SCHOOL |  | F- IM Completed
MaynardPS | MAYNARD | 2018-05-22 | 2174000 | N | N | 01740505 | Maynard High | SCHOOL |  | F- IM Completed
NarragansetRSD | BALDWINVILLE | 2018-05-16 | 2294000 | N | N | 07200005 | Baldwinville Elementary School | SCHOOL |  | H- Ready to schedule IM
NarragansetRSD | BALDWINVILLE | 2018-05-16 | 2294000 | N | N | 07200305 | Narragansett Middle School | SCHOOL |  | H- Ready to schedule IM
NarragansetRSD | BALDWINVILLE | 2018-05-16 | 2294000 | N | N | 07200505 | Narragansett Regional High School | SCHOOL |  | H- Ready to schedule IM | [7 empty] | 0
AgawamPS | AGAWAM | 2018-06-08 | 1005000 | N | N | 00050003 | Agawam Early Childhood Center | SCHOOL |  | I- Fall Sampling? | completed |  | 13 | 26
AgawamPS | AGAWAM | 2018-06-08 | 1005000 | N | N | 00050505 | Agawam High School | SCHOOL |  | I- Fall Sampling? | completed |  | 35 | 70
AgawamPS | FEEDING HILLS | 2018-06-08 | 1005000 | N | N | 00050405 | Agawam Junior High School | SCHOOL |  | I- Fall Sampling? | completed |  | 43 | 86
AgawamPS | AGAWAM | 2018-06-08 | 1005000 | N | N | 00050020 | Benjamin J Phelps Elementary School | SCHOOL |  | I- Fall Sampling? | completed |  | 44 | 88
AgawamPS | FEEDING HILLS | 2018-06-08 | 1005000 | N | N | 00050010 | Clifford M Granger Elementary School | SCHOOL |  | I- Fall Sampling? | completed |  | 59 | 118
AgawamPS | AGAWAM | 2018-06-08 | 1005000 | N | N | 00050030 | James Clark Elementary School | SCHOOL |  | I- Fall Sampling? | completed |  | 56 | 112
AgawamPS | AGAWAM | 2018-06-08 | 1005000 | N | N | 00050303 | Roberta G Doering School | SCHOOL |  | I- Fall Sampling? | completed |  | 24 | 48
AgawamPS | AGAWAM | 2018-06-08 | 1005000 | N | N | 00050025 | Robinson Park Elementary School | SCHOOL |  | I- Fall Sampling? | completed |  | 60 | 120 |  |  |  | 668
Amesbury PS | AMESBURY | 2018-05-23 | 3007000 | N | N | 00070005 | Amesbury Elementary | SCHOOL |  | J- Waiting List
Amesbury PS | AMESBURY | 2018-05-23 | 3007000 | N | N | 00070505 | Amesbury High | SCHOOL |  | J- Waiting List
Amesbury PS | AMESBURY | 2018-05-23 | 3007000 | N | N | 00070515 | Amesbury Innovation High School | SCHOOL |  | J- Waiting List
Amesbury PS | AMESBURY | 2018-05-23 | 3007000 | N | N | 00070013 | Amesbury Middle | SCHOOL |  | J- Waiting List
Amesbury PS | AMESBURY | 2018-05-23 | 3007000 | N | N | 00070010 | Charles C Cashman Elementary | SCHOOL |  | J- Waiting List
NMRSD | PEPPERELL | 2018-05-23 | 2299000 | N | N | 07350505 | North Middlesex Regional High School | SCHOOL |  | J- Waiting List
St Vincent's Home | FALL RIVER | 2018-05-23 | 4095000 | N | N | 00950940 | Saint Vincent’s | EECF |  | J- Waiting List
Weston PS | WESTON | 2018-05-23 | 3333000 | N | Y | 03300010 | Country | SCHOOL |  | J- Waiting List
Weston PS | WESTON | 2018-05-23 | 3333000 | N | Y | 03300012 | Field Elementary School | SCHOOL |  | J- Waiting List
Weston PS | WESTON | 2018-05-23 | 3333000 | N | Y | 03300505 | Weston High | SCHOOL |  | J- Waiting List
Weston PS | WESTON | 2018-05-23 | 3333000 | N | Y | 03300305 | Weston Middle | SCHOOL |  | J- Waiting List
Weston PS | WESTON | 2018-05-23 | 3333000 | N | Y | 03300015 | Woodland | SCHOOL |  | J- Waiting List
AbingtonPS | ABINGTON | 2017-12-19 | 4001000 | N | N |  | Pre-K/Middle/High School | SCHOOL |  | K- Advice Only | advice only
LongmeadowPS | LONGMEADOW | 2018-04-30 | 1159000 | N | N | 01590005 | Blueberry Hill | SCHOOL |  | K- Advice Only | advice only
LongmeadowPS | LONGMEADOW | 2018-04-30 | 1159000 | N | N | 01590010 | Center | SCHOOL |  | K- Advice Only | advice only
LongmeadowPS | LONGMEADOW | 2018-04-30 | 1159000 | N | N | 01590017 | Glenbrook Middle | SCHOOL |  | K- Advice Only | advice only
LongmeadowPS | LONGMEADOW | 2018-04-30 | 1159000 | N | N | 01590505 | Longmeadow High | SCHOOL |  | K- Advice Only | advice only
LongmeadowPS | LONGMEADOW | 2018-04-30 | 1159000 | N | N | 01590305 | Williams Middle | SCHOOL |  | K- Advice Only | advice only
LongmeadowPS | LONGMEADOW | 2018-04-30 | 1159000 | N | N | 01590025 | Wolf Swamp Road | SCHOOL |  | K- Advice Only | advice only
ReverePS | REVERE | 2018-03-15 | 3248000 | N | Y | 02480025 | Abraham Lincoln Elementary School | SCHOOL |  | K- Advice Only | advice only
ReverePS | REVERE | 2018-03-22 | 3248000 | N | Y | 02480056 | Garfield Elementary School | SCHOOL |  | K- Advice Only | advice only
ReverePS | REVERE | 2018-03-22 | 3248000 | N | Y | 02480057 | Garfield Middle School | SCHOOL |  | K- Advice Only | advice only
ReverePS | REVERE | 2017-09-12 | 3248000 | N | Y | 02480505 | Revere High School | SCHOOL |  | K- Advice Only | advice only
BRRSD | BRIDGEWATER | 2018-02-13 | 4042000 | N | N | 06250002 | George H Mitchell Elementary School | SCHOOL |  | O- Out of program | Out of Program | Out of Program |  |  | Out of Program | Out of Program | Out of Program |  | NA
Canton Preschool | CANTON | 2018-03-26 | 4050000 | N | N | 2911982 | The Learning Circle Preschool Inc. | EECF |  | O- Out of program | Out of Program | Out of Program |  |  | Out of Program | Out of Program | Out of Program |  | NA
CCCDP | BOURNE | 2018-04-05 | 4020014 | N | N | 211758 | Cape Cod Child Development Bourne Head Start Preschool | EECF |  | O- Out of program | Out of Program | Out of Program |  |  | Out of Program | Out of Program | Out of Program |  | NA
CCCDP | BARNSTABLE | 2018-04-05 | 4020013 | N | N |  | Cape Cod Child Development Centerville Head Start Preschool | EECF |  | O- Out of program | Out of Program | Out of Program |  |  | Out of Program | Out of Program | Out of Program |  | NA
CCCDP | DENNIS PORT | 2018-04-05 | 4020007 | N | N | 200093 | Cape Cod Child Development Dennisport Preschool | EECF |  | O- Out of program | Out of Program | Out of Program |  |  | Out of Program | Out of Program | Out of Program |  | NA
CCCDP | FALMOUTH | 2018-04-05 | 4020012 | N | N | 300660 | Cape Cod Child Development Falmouth School Age | EECF |  | O- Out of program | Out of Program | Out of Program |  |  | Out of Program | Out of Program | Out of Program |  | NA
CCCDP | HYANNIS | 2018-04-05 | 4020011 | N | N |  | Cape Cod Child Development Preschool | EECF |  | O- Out of program | Out of Program | Out of Program |  |  | Out of Program | Out of Program | Out of Program |  | NA
CCCDP | FALMOUTH | 2018-04-05 | 4020009 | N | N | 2912002 | Cape Cod Child Development/Falmouth Preschool | EECF |  | O- Out of program | Out of Program | Out of Program |  |  | Out of Program | Out of Program | Out of Program |  | NA
CCCDP | WEST YARMOUTH | 2018-04-05 | 4020008 | N | N | 290671 | Cape Cod Child Development/West Yarmouth Preschool and School Age | EECF |  | O- Out of program | Out of Program | Out of Program |  |  | Out of Program | Out of Program | Out of Program |  | NA
CCCDP | HYANNIS | 2018-04-05 | 4020004 | N | N | 200044 | Cape Cod Child Development-Hyannis Preschool | EECF |  | O- Out of program | Out of Program | Out of Program |  |  | Out of Program | Out of Program | Out of Program |  | NA
CCCDP | HYANNIS | 2018-04-05 | 4020006 | N | N | 300189 | Cape Cod Child Development-Hyannis School Age | EECF |  | O- Out of program | Out of Program | Out of Program |  |  | Out of Program | Out of Program | Out of Program |  | NA
CCCDP | HYANNIS | 2018-04-05 | 4020005 | N | N | 200047 | Cape Cod Child Development-Stevens Street Preschool | EECF |  | O- Out of program | Out of Program | Out of Program |  |  | Out of Program | Out of Program | Out of Program |  | NA
CCCDP | WAREHAM | 2018-04-05 | 4020010 | N | N | 200286 | Cape Cod Child Development-Wareham Preschool | EECF |  | O- Out of program | Out of Program | Out of Program |  |  | Out of Program | Out of Program | Out of Program |  | NA
ClintonPS | CLINTON | 2018-01-17 | 2064000 | N | Y |  | Administration Building | EECF |  | O- Out of program | out of program | Out of Program |  |  | Out of Program | Out of Program |  |  | NA
LeominsterPS | LEOMINSTER | 2018-01-31 | 2153000 | a | N | 01530605 | Center For Technical Education Innovation | SCHOOL |  | O- Out of program | Out of Program | Out of Program |  |  | Out of Program | Out of Program | Out of Program |  | NA | [11 empty] | Part of High School
LeominsterPS | LEOMINSTER | 2018-01-31 | 2153000 | N | N | 01530515 | Leominster Center for Excellence | SCHOOL |  | O- Out of program | Out of Program | Out of Program |  |  | Out of Program | Out of Program | Out of Program |  | NA | [11 empty] | no potable water taps
MillisPS | MILLIS | 2018-03-15 | 2187000 | N | N | 01870505 | Millis High School | SCHOOL |  | O- Out of program | Out of program | Out of Program |  |  | Out of Program | Out of Program | Out of Program |  | NA
PittsfieldPS | PITTSFIELD | 2018-05-15 | 1236000 | N | N | 02360510 | Taconic High School | SCHOOL |  | O- Out of program | Out of Program | Out of Program |  |  |  | Out of Program | Out of Program |  | NA | [7 empty] | Will not be sampled this year, under renovation
RandolphPS | RANDOLPH | 2018-05-10 | 4244000 | N | N | 02440020 | Elizabeth G Lyons Elementary School | SCHOOL |  | O- Out of program | Out of Program | Out of Program |  |  | Out of Program | Out of Program | out of program |  | NA
RandolphPS | RANDOLPH | 2018-05-10 | 4244000 | N | N | 02440018 | J F Kennedy Elementary School | SCHOOL |  | O- Out of program | Out of Program | Out of Program |  |  | Out of Program | Out of Program | out of program |  | NA
RandolphPS | RANDOLPH | 2018-05-10 | 4244000 | N | N | 02440015 | Margaret L Donovan Elementary School | SCHOOL |  | O- Out of program | Out of Program | Out of Program |  |  | Out of Program | Out of Program | out of program |  | NA
RandolphPS | RANDOLPH | 2018-05-10 | 4244000 | N | N | 02440040 | Martin E Young Elementary School | SCHOOL |  | O- Out of program | Out of Program | Out of Program |  |  | Out of Program | Out of Program | out of program |  | NA
RandolphPS | RANDOLPH | 2018-05-10 | 4244000 | N | N | 02440410 | Randolph Community Middle School | SCHOOL |  | O- Out of program | Out of Program | Out of Program |  |  | Out of Program | Out of Program | out of program |  | NA
RandolphPS | RANDOLPH | 2018-05-10 | 4244000 | N | N | 02440505 | Randolph High School | SCHOOL |  | O- Out of program | Out of Program | Out of Program |  |  | Out of Program | Out of Program | out of program |  | NA
ReadingPS | READING | 2018-03-16 | 3246000 | N | Y | 02460017 | J. Warren Killam Elementary School | SCHOOL |  | O- Out of program | Out of Program | Out of Program |  |  | Out of Program | Out of Program | out of program |  | NA
WalthamCCC | WALTHAM | 2018-03-15 | 3308000 | N | Y | 200454 | Waltham Child Care Center | EECF |  | O- Out of program | Out of program | Out of Program |  |  | Out of Program | Out of Program | Out of Program |  | NA
WeymouthPS | WEYMOUTH | 2018-03-01 | 4336022 | N | N | 03360310 | Abigail Adams Middle School | SCHOOL |  | O- Out of program | Out of Program | Out of Program |  |  | Out of Program | Out of Program | Out of Program |  | NA
WeymouthPS | WEYMOUTH | 2018-04-11 | 4336010 | N | N |  | Administration Building | EECF |  | O- Out of program | Out of Program | Out of Program |  |  | Out of Program | Out of Program | Out of Program |  | NA
WeymouthPS | WEYMOUTH | 2018-04-11 | 4336011 | N | N |  | Administration Building | EECF |  | O- Out of program | Out of Program | Out of Program |  |  | Out of Program | Out of Program | Out of Program |  | NA
WeymouthPS | WEYMOUTH | 2018-04-11 | 4336012 | N | N | 03360050 | Frederick C Murphy Primary School | SCHOOL |  | O- Out of program | Out of Program | Out of Program |  |  | Out of Program | Out of Program | Out of Program |  | NA
WeymouthPS | WEYMOUTH | 2018-04-11 | 4336013 | N | N | 03360003 | Johnson Early Childhood Center | SCHOOL |  | O- Out of program | Out of Program | Out of Program |  |  | Out of Program | Out of Program | Out of Program |  | NA
WeymouthPS | WEYMOUTH | 2018-04-11 | 4336014 | N | N | 03360065 | Lawrence W Pingree Primary School | SCHOOL |  | O- Out of program | Out of Program | Out of Program |  |  | Out of Program | Out of Program | Out of Program |  | NA
WeymouthPS | WEYMOUTH | 2018-04-11 | 4336015 | N | N | 03360020 | Maria Weston Chapman Middle School | SCHOOL |  | O- Out of program | Out of Program | Out of Program |  |  | Out of Program | Out of Program | Out of Program |  | NA
WeymouthPS | WEYMOUTH | 2018-04-11 | 4336020 | N | N | 03360085 | Ralph Talbot Primary School | SCHOOL |  | O- Out of program | Out of Program | Out of Program |  |  | Out of Program | Out of Program | Out of Program |  | NA
WeymouthPS | WEYMOUTH | 2018-04-11 | 4336016 | N | N | 03360060 | Thomas V Nash Jr. Primary School | SCHOOL |  | O- Out of program | Out of Program | Out of Program |  |  | Out of Program | Out of Program | Out of Program |  | NA
WeymouthPS | WEYMOUTH | 2018-04-11 | 4336021 | N | N | 03360105 | Thomas W Hamilton Primary School | SCHOOL |  | O- Out of program | Out of Program | Out of Program |  |  | Out of Program | Out of Program | Out of Program |  | NA
WeymouthPS | WEYMOUTH | 2018-04-11 | 4336019 | N | N | 03360110 | Wessagusset Primary School | SCHOOL |  | O- Out of program | Out of Program | Out of Program |  |  | Out of Program | Out of Program | Out of Program |  | NA
WeymouthPS | WEYMOUTH | 2018-04-11 | 4336017 | N | N | 03360505 | Weymouth High School | SCHOOL |  | O- Out of program | Out of Program | Out of Program |  |  | Out of Program | Out of Program | Out of Program |  | NA
WeymouthPS | WEYMOUTH | 2018-04-11 | 4336018 | N | N | 03360080 | William Seach Primary School | SCHOOL |  | O- Out of program | Out of Program | Out of Program |  |  | Out of Program | Out of Program | Out of Program |  | NA
All Done | A
Sampling done | B
sampling scheduled | C
Sampling> June 1? | D
Sample plan done | E
IM Completed | F
IM Scheduled | G
Ready to schedule IM | H
Fall Sampling? | I
Waiting List | J
Advice Only | K
Out of program | O

## Contacts
Date Record Updated | Notes | Admin Unit | Location | PPC First Name | PPC Last Name | PPC Title | PPC Phone | PPC Address | PPC Email | Municipal Official | PWS Contact | Regional DEP Contact | TAP Email | Facility Personnel
2017-12-19 | Spoke on phone | AbingtonPS | ABINGTON | Jason | Linn | Maintenance Director | 781-982-2154 | 1071 Washington St., Abington, MA 02351 | jasonlinn@abingtonps.org | rlafond@abingtonma.gov | dcallahan@abrockwater.com | Richard.Rondeau@state.ma.us | rlarson@umass.edu
2018-06-08 | Rick spoke w/ Doug White | AgawamPS | AGAWAM | Steve | Lemanski | Superintendent of Schools | 413-821-0552 | 1305 Springfield St., Feeding Hills, MA 01030 | slemanski@agawamed.org | mayor@agawam.ma.us | cgolba@agawam.ma.us | Deirdre.Doherty@state.ma.us | robert.hoyt@state.ma.us | Norm, Robbins, Principal, nrobbins@agawamed.org ¦Cheryl, Salomeo, Principal, csalomeo@agawamed.org ¦Susan, Federico, Principal, sfederico@agawamed.org ¦Shelley, Russell, Principal, srussell@agawamed.org ¦Noelle, Colbert, Principal, ncolbert@agawamed.org ¦Thomas , Schnepp, Principal, tschnepp@agawamed.org ¦Robin, Fernandes, Director, rfernandes@agawamed.org ¦
2018-05-17 | All Results sent | BaystateACPS | SPRINGFIELD | Tim | Sneed | Executive Director | 413-366-5103 | 2001 Roosevelt Ave., Springfield, MA 01104 | tsneed@bacps.net | msarno@springfieldcityhall.com | josh.schimmel@waterandsewer.org | Deirdre.Doherty@state.ma.us | rlarson@umass.edu | Tim, Sneed, Executive Director, tsneed@bacps.net ¦ Isabel, Cartagena, Business Manager, icartagena@bacps.net ¦
2018-05-09 | IM completed | BraintreePS | BRAINTREE | Edward | Cronin | Director of Finance and Operations | 781-794-8482 | 348 Pond St., Braintree, MA 02184 | ecronin@braintreema.gov | mayorsoffice@braintreema.gov | ldutton@braintreema.gov | Richard.Rondeau@state.ma.us | yaskmenow1983@gmail.com | Edward, Cronin, Director of Finance and Operations, ecronin@braintreema.gov ¦
2018-04-19 | IM completed | BRRSD | BRIDGEWATER | Paul | Fox | Director of Facilities | 508-279-2140 | 166 Mt Prospect St., Bridgewater, MA 02324 | pfoxjr@bridge-rayn.org | TownManager@bridgewaterma.org | wmwardrcwd@comcast.net/jkazlauskas@bridgewaterma.org | Richard.Rondeau@state.ma.us | tombienk58@gmail.com | Paul, Fox, Director of Facilities, pfoxjr@bridge-rayn.org ¦
2018-04-27 | Out of Program | Canton Preschool | CANTON | Katrina | Selawsky | Director | 781-828-4800 | 3 Blue Hill River Road, Canton, MA 02021 | info@learningcirclepreschool.org | bos@town.canton.ma.us | mtrotta@town.canton.ma.us | Richard.Rondeau@state.ma.us | out of program | Katrina, Selawsky, Director, info@learningcirclepreschool.org ¦
2018-05-10 | Out of Program | CCCDP | HYANNIS | Michael | Scarpellini | Director of Youth and Support Services | 508-775-6240 | 83 Pearl St., Hyannis, MA 02601 | mscarpellini@cccdp.org | email@town.barnstable.ma.us,townmanager@falmouthmass.us | hans.keijser@town.barnstable.ma.us | Richard.Rondeau@state.ma.us | tombienk58@gmail.com | Michael, Scarpellini, Director , mscarpellini@cccdp.org ¦
2018-04-30 | IM scheduled | Children's Workshop | CUMBERLAND RI | Nicole | Chiello | VP, Regional Director of Operations | 401-580-7738 | 45 Industrial Road | nchiello@childrensworkshop.com | selectmen@town.westborough.ma.us | wparks@wbridgewater.com | Richard.Rondeau@state.ma.us | yaskmenow1983@gmail.com,tombienk58@gmail.com> | Amanda, Miller, Director, wbridgewater@childrensworkshop.com ¦
2018-05-23 | All Results sent | ClintonPS | CLINTON | Russell | Karlstad | Director of Public Facilities | 978-365-4114 | 242 Church Street, Cinton, MA 01510 | rkarlstad@clintonma.gov | mward@clintonma.gov | cmcgown@clintonma.gov | Robert.Bostwick@state.ma.us | llaine911@gmail.com | Russell, Karlstad, Director of Public Facilities, rkarlstad@clintonma.gov ¦
2018-03-27 | All Results sent | GraftonPS | GRAFTON | Anthony | LeMay | Director of Buildings and Grounds | 508-735-2166 | 30 Providence Rd, Grafton, MA 01519 | lemaya@grafton.k12.ma.us | mcinerneyt@grafton-ma.gov | graftonh20@aol.com | Robert.Bostwick@state.ma.us | llaine911@gmail.com | Anthony, Lemay, Director of Buildings and Grounds, lemaya@grafton.k12.ma.us ¦
2018-05-23 | Sampling completed | HaverhillComAct | HAVERHILL | Jill | Sullivan | Operations Manager | 978-372-5052 x447 | 75 Elm St., Haverhill, MA 01830 | jsullivan@communityactioninc.org | mayor@cityofhaverhill.com | rward@haverhillwater.com | Thomas.Mahin@state.ma.us | yaskmenow1983@gmail.com | Jill, Sullivan, Operations Manager, jsullivan@communityactioninc.org ¦ Kerry Perry, kperry@communityactioninc.org
2017-11-13 | All Results sent | LeominsterPS | LEOMINSTER | Anthony | Sciabarrasi | Facility Director | 978 534 7700 x 332 | 24 Church St., Leominster, MA 01453 | anthony.sciabarrasi@leominster.mec.edu | dmazzarella@leominster-ma.gov | robert.chalifoux@veolia.com | Robert.Bostwick@state.ma.us | yaskmenow1983@gmail.com | anthony, sciabarrasi, facility director, anthony.sciabarrasi@leominster.mec.edu ¦
2018-05-23 | Sample plans completed | Little Folks | EAST BOSTON | Marie | Bossi | Executive Director | 617-569-0294 | 65 Trenton Street | little.folks@aol.com | mayor@cityofboston.gov | sullivanjp@bwsc.org | Thomas.Mahin@state.ma.us | robert.hoyt@state.ma.us | Marie, Bossi, Executive Director, little.folks@aol.com ¦ Michelle, Gill, Education Supervisor, little.folks@aol.com ¦
2018-05-02 | Sent ack. Email | LongmeadowPS | LONGMEADOW | John | Cloonan | Facilities Director - Town of Longmeadow | 413-567-3400 | 31 Pondside Rd, Longmeadow, MA 01106 | jcloonan@longmeadow.org | Townhall@longmeadow.org | pthurber@longmeadow.org | Deirdre.Doherty@state.ma.us |  | Todd , Carney, Facilities Foreman, tcarney@longmeadow.k12.ma.us ¦
2018-05-14 | Sampling completed | LudlowPS | LUDLOW | Darlene | Cincone | Dir. of Oper./Asst, Business Mgr. | 413-583-5663 ext 106 | 63 Chestnut St., Ludlow, MA 01056 | d_cincone@ludlowps.org | selectmen@Ludlow.ma.us | josh.schimmel@waterandsewer.org | Deirdre.Doherty@state.ma.us | vdkiken@comcast.net | Michael, Bertini, District Facilities Coordinator, m_bertini@ludlowps.org ¦
2018-06-04 | Sampling completed | LunenburgPS | LUNENBURG | John | Londa | Director of Facilities | 978-230-2351 | 1025 Mass. Ave., Lunenburg, MA 01462 | jlonda@lunenburgonline.com | bos@lists.lunenburgonline.com | FMcNamara@Lunenburgwater.net | Robert.Bostwick@state.ma.us | yaskmenow1983@gmail.com | John, Londa, Director of Facilities, jlonda@lunenburgonline.com ¦
2018-05-10 | Sampling scheduled | LynnfieldPS | LYNNFIELD | Anthony | Fratoni | Assistant Director of School Operations | 781-334-9501 | 55 Summer St., Lynnfield, MA 01940 | tfratoni@town.lynnfield.ma.us | (781) 334-9400 | jfinegan@lwdma.us | Thomas.Mahin@state.ma.us | yaskmenow1983@gmail.com | Steve , DeBettencourt, Assistant Director of Facilities, sdebettencourt@town.lynnfield.ma.us ¦
2017-11-09 | All Results sent | MansfieldPS | MANSFIELD | Edward | Donoghue | Asst. Superintendent for Finance & Operations | 505-261-7506 | 2 Park Row, Mansfield, MA 02048 | edward.donoghue@mansfieldschools.com | townmanager@mansfieldma.com | kgaffney@mansfieldma.com | Richard.Rondeau@state.ma.us | yaskmenow1983@gmail.com | Matthew, Jacques, Director of Facilities, matthew.jacques@mansfieldschools.com ¦
2018-05-21 | IM scheduled | MasconometRSD | BOXFORD | Douglas | Batchelder | Director of Operations | 978-423-8390 | 20 Endicott Rd, Boxford, MA 01921 | dbatchelder@masconomet.org | abenson@town.boxford.ma.us | none | Thomas.Mahin@state.ma.us | robert.hoyt@state.ma.us | Douglas, Batchelder, Director of Operations, dbatchelder@masconomet.org ¦
2018-08-24 | Rick spoke w/ Tim Goulding | MaynardPS | MAYNARD | Aaron | Miklosko | Director of Public Works | 978-897-1308 | 195 Main Street, Maynard, MA 01754 | amiklosko@townofmaynard.net | AScribner@townofmaynard.net | amiklosko@townofmaynard.net | Robert.Bostwick@state.ma.us |  | Aaron, Miklosko, Director of Public Works, amiklosko@townofmaynard.net ¦
2018-04-27 | Out of Program | MillisPS | MILLIS | John | Engler | Director of Operations | 508-376-7013 | 245 Plain St., Millis, MA 02054 | jengler@millisps.org | kbouret@millis.net | jmckay@millis.net | Robert.Bostwick@state.ma.us |  | John, Engler, Facilities Director, jengler@millisps.org ¦
2018-05-29 | Ready to schedule IM, emailed him a reminder | NarragansetRSD | BALDWINVILLE | Rick | Moulton | Director of Buildings and Grounds | 978-895-9381 | 462 Baldwinville Rd, Baldwinville, MA 01436 | rmoulton@nrsd.org | townadministrator@templeton1.org | rdavan@templetonlight.com | Robert.Bostwick@state.ma.us |  | Rick, Moulton, Facilities Director NRSD, rmoulton@nrsd.org ¦
2017-09-12 | All Results sent | NashValTSD | WESTFORD | Jeanne | Savoie | Business Manager | 978-692-4711 x 11174 | 100 Littleton Rd, Westford, MA 01886 | jsavoie@nashobatech.net | jross@westfordma.gov | scronin@westfordma.gov | Thomas.Mahin@state.ma.us | yaskmenow1983@gmail.com | Jeanne, Savoie, Business Manager, jsavoie@nashobatech.net ¦ Paul, Jussaume, Director of Vocational Operations/Facilities, pjussaume@nashobatech.net ¦
2018-06-04 | Sampling completed | North ReadingPS | NORTH READING | Wayne | Hardacker | Supervisor of Buildings & Grounds | 978-360-1687 | 189 Park St., North Reading, MA 01864 | whardacker@nrpsk12.org | mgilleberto@northreadingma.gov | mclark@northreadingma.gov | Thomas.Mahin@state.ma.us | yaskmenow1983@gmail.com | Wayne, Hardacker, Supervisor of Buildings & Grounds, whardacker@nrpsk12.org ¦
2017-12-13 | All Results sent | NRSD | BOLTON | Robert | Frieswick | Interim Facilities Manager | 978-779-0539 | 50 Mechanic St., Bolton, MA 01740 | rfrieswick@nrsd.net | rczekanski@townofbolton.biz | JCONVERSE@NRSD.NET | Robert.Bostwick@state.ma.us | yaskmenow1983@gmail.com | Robert , Freiswick, Interim Facilities Manager, rfreiswick@nrsd.net ¦ Patricia, Marone, Interim Business and Operations Manager, pmarone@nrsd.net ¦
2018-04-20 | All Results sent | NSWSD | NEW SALEM | Larry | Ramsdell | Director of Maintenance | 978-544-6926 | 201 Wendell Rd, New Salem, MA 01355 | ramsdell@swiftriverschool.org | towncoord@crocker.com | ramsdell@swiftriverschool.org | Deirdre.Doherty@state.ma.us | vdkiken@comcast.net | Larry, Ramsdell, Director of Maintenance, ramsdell@swiftriverschool.org ¦
2018-06-04 | Sampling completed | PittsfieldPS | PITTSFIELD | James | Esoldi | LEA / Project Supervisor | 413-281-3158 | 81 Hawthorne Ave., Pittsfield, MA 01201 | jesoldi@cityofpittsfield.org | mayorsoffice@pittsfieldch.com | bstack@cityofpittsfield.org | Deirdre.Doherty@state.ma.us | vdkiken@comcast.net | James, Esoldi, LEA/Project Suprevisor, jesoldi@cityofpittsfield.org ¦
2018-05-14 | Sampling scheduled | PositiveRegard | HOLYOKE | Peter | Miller | Director of Administrative Operations | 413-533-9500 | 1913 Northampton St., Holyoke, MA 01040 | pmiller@positiveregard.com | morsea@holyoke.org | contid@holyoke.org | Deirdre.Doherty@state.ma.us | vdkiken@comcast.net | Peter, Miller, Director of Administrative Operations, pmiller@positiveregard.com ¦
2018-05-14 | Out of Program | RandolphPS | RANDOLPH | Richard | Brewer | DPW Superintendent | 781-961-0942 | 41 S. Main St., Randolph, MA 02368 | rbrewer@randolph-ma.gov | dmurphy@randolph-ma.gov | rbrewer@randolph-ma.gov | Richard.Rondeau@state.ma.us |  | Mike, Caliri, Maintenance Director, calirim@randolph.ma.gov ¦
2017-10-06 | Rick helped with Tool | ReadingPS | READING | Erik | Mysliwy | Water Quality and Supply Coordinator | 781-858-2566 | 16 Lowell St., Reading, MA 01867 | emysliwy@ci.reading.ma.us | townmanager@ci.reading.ma.us | jzager@ci.reading.ma.us | Thomas.Mahin@state.ma.us | rlarson@umass.edu | Erik, Mysliwy, Water Quality & Supply Coordinator, emysliwy@ci.reading.ma.us ¦
2017-11-16 | Spoke w/ Martelli, they sampled already w/ MWRA | ReverePS | REVERE | Carl | Svendsen | Director of Plant and Maintenance | 781-286-8226 | 101 School St., Revere, MA 02151 | csvendsen@revere.mec.edu | revere_mayor@revere.org | mamartelli@revere.org | Thomas.Mahin@state.ma.us | rlarson@umass.edu | Carl, Svendsen, Director of Maintenance and Facilities, csvendsen@revere.mec.edu ¦
2018-05-10 | IM completed | SBRSD | SHEFFIELD | Jeremy | Wells | Director of Buildings, Grounds, and Food Services | 413-229-8778 x 158 | 491 Berkshire School Road, Sheffield, MA 01257 | jwells@sbrsd.org | rlabombard@sheffieldma.gov | Travis Helming | Deirdre.Doherty@state.ma.us | vdkiken@comcast.net | Jeremy , Wells, Director of Buildings and Grounds , jwells@sbrsd.org ¦
2018-04-11 | IM completed | SEBRSD | SPENCER | Eric | Hevy | Supervisor Buildings & Grounds | 508-885-8500 x9 | 306 Main St., Spencer, MA 01562 | hevye@sebrsd.org | tpepe@spencerma.gov | gkarpowicz@spencerma.gov | Robert.Bostwick@state.ma.us | llaine911@gmail.com | Eric, Hevey, Supervisor Buildings & Grounds, heveye@sebrsd.org ¦Gary Suter, Business Director, suterg@sebrsd.or
2018-05-03 | IM scheduled | SelfHelp | BROCKTON | Frances | Reid | ERSEA/Ancillary Services Manager | 508-587-1716 | 370 Howard Street, Brockton, MA 02302 | freid@selfhelpinc.org | BillCarpenter@cobma.us | michael.sessine@veolia.com | Richard.Rondeau@state.ma.us | yaskmenow1983@gmail.com | Frances, Freid, ERSEA/Ancillary Services Manager, freid@selfhelpinc.org ¦
2018-05-15 | IM scheduled | Shutesbury ES | SHUTESBURY | Jacqueline | Mendonsa | Principal | 413-259-1212 x 111 | 23 West Pelham Rd, Shutesbury, MA 01072 | mendonsaj@shutesburyschool.org | townadmin@shutesbury.org | Robert Mahler | Deirdre.Doherty@state.ma.us | tobiason | Matthew, Foster, Head Custodian, fosterm@shutesburyschool.org ¦
2018-06-04 | Sample plans completed | South Hadley PS | SOUTH HADLEY | Nicholas | Young | Superintendent of Schools | 413-538-5060 | 116 Main Street, South Hadley, MA 01075 | NYoung@shschools.com | selectboard@southhadleyma.gov | maiken@comcast.net | Deirdre.Doherty@state.ma.us | vdkiken@comcast.net | Nicholas, Young, Superintendent of Schools, NYoung@shschools.com ¦
2018-06-04 | All Results sent | SouthShoreCPS | NORWELL | Mark | Flanagan | Fac Dir | 781-982-4202 x105 | 100 Longwater Cir., Norwell, MA 02061 | mflanagan@sscps.org | pmorin@townofnorwell.net | JOHNMCINNIS@COMCAST.NET | Richard.Rondeau@state.ma.us | tombienk58@gmail.com | Mark, Flanagan, Fac Dir, mflanagan@sscps.org ¦
2018-02-13 | All Results sent | StoughtonPS | STOUGHTON | Joel | Harding | Director Maintenance & Operations | 508-326-9666 | 232 Pearl Street, Stoughton, MA 02072 | j_harding@stoughtonschools.org | mtisdelle@stoughton-ma.gov | pmcnulty@stoughton-ma.gov | Richard.Rondeau@state.ma.us | yaskmenow1983@gmail.com | Joel, Harding, Director Maintenance & Operations, j_harding@stoughtonschools.org ¦
2018-05-23 | Sample plans completed | SudburyPS | SUDBURY | Joseph | Kupczewski | Maintenance Director | 978-423-0060 | 275 Old Lancaster Rd, Sudbury, MA 01776 | joe_kupczewski@sudbury.k12.ma.us | bilodeaum@sudbury.ma.us | rmcenroe@sudburywater.com | Thomas.Mahin@state.ma.us | llaine911@gmail.com
2018-05-25 | IM completed | TantasquaRSD | FISKDALE | Richard | Wetherbee II | District Facilities Manager | 508-347-3077 | 320A Brookfield Rd, Fiskdale, MA 01518 | wetherbeer@tantasqua.org | selectmen@brimfieldma.org, selectmen@townofholland.necoxmail.com | TAP needs to find out | Deirdre.Doherty@state.ma.us | yaskmenow1983@gmail.com,tombienk58@gmail.com> | Richard, Wetherbee II, District Facilties Manager, wetherbeer@tantasqua.org ¦ Bruce, Stearns, Maintenance Lead, stearnsb@tantasqua.org ¦Jayson , Findlay, Maintenance Lead, findlayj@tantasqua.org ¦
2018-04-10 | Sampling completed | TEC-COOP | EAST WALPOLE | Elizabeth | McGonagle | Executive Director | 781-352-5711 | 141 Mansion Drive, Suite 200, E. Walpole, MA 02032 | lmcgonagle@tec-coop.org | jjohnson@walpole-ma.gov | rmattson@walpole-ma.gov | Richard.Rondeau@state.ma.us | yaskmenow1983@gmail.com,tombienk58@gmail.com> | Daniel , Shovak, Director of Finance & Operations, dshovak@tec-coop.org ¦
2018-04-20 | All Results sent | TritonRSD | BYFIELD | Christopher | Walsh | Facility & Grounds Manager | 978-518-4207 | 112 Elm St., Byfield, MA 01922 | christopher.walsh@tritonschools.org | info@townofnewbury.org | byfieldwater@comcast.net | Thomas.Mahin@state.ma.us | yaskmenow1983@gmail.com,tombienk58@gmail.com> | Christopher, Walsh, Facilities & Grounds Manager, christopher.walsh@tritonschools.org ¦ Steve, Orme, Head Custodian, steven.orme@tritonschools.org ¦ Michelle , Cresta, School Business Administrator, michelle.cresta@tritonschools.org ¦
2018-05-21 | IM scheduled | Tri-Town SU | BOXFORD | Steve | Clifford | Director of Facilities | 978-887-0771 | 28 Middleton Road, Boxford, MA 01921 | sclifford@tritownschoolunion.com | abenson@town.boxford.ma.us | gkrom@topsfield-ma.gov | Thomas.Mahin@state.ma.us | robert.hoyt@state.ma.us | Steve , Clifford, Director of Facilities, sclifford@tritownschoolunion.com ¦
2018-02-20 | All Results sent | UMassAmherstCEEC | AMHERST | Maryanne | Baskin | Director | 413-545-1566 | 21 Clubhouse Dr., Amherst, MA 01003 | mbaskin@umass.edu | townmanager@amherstma.gov | mooringg@amherstma.gov | Deirdre.Doherty@state.ma.us | rlarson@umass.edu | Maryanne, Baskin, Director, mbaskin@umass.edu ¦ Teresa, Houle, Office Supervisor, thoule@umass.edu ¦
2017-12-04 | Sampling completed | WachusettRSD | JEFFERSON | James | Covello | Pre-12 Facilities Manager | 508-667-6350 | 1745 Main St., Jefferson, MA 01522 | jim_covello@wrsd.net | plukes@holdenma.gov | rmouradian@holdenma.gov | Robert.Bostwick@state.ma.us | yaskmenow1983@gmail.com | Tony, Cipro, Principal, tony_cipro@wrsd.net ¦
2018-04-27 | Out of Program | WalthamCCC | WALTHAM | kai | Tao | Director | 617-335-0606 | 411 Waverley Oaks Rd Suite 214, Waltham, MA 02452 | kaitao00@gmail.com | mayor@city.waltham.ma.us | scasazza@city.waltham.ma.us | Thomas.Mahin@state.ma.us |  | kai, Tao, Director, kaitao00@gmail.com ¦
2018-03-27 | Results posted on Tool, need them from DEP | WestboroughPS | WESTBOROUGH | Steven | Baccari | Director of Public Health | 508-366-3045 | 34 West Main St., Westborough, MA 01581 | sbaccari@town.westborough.ma.us | jmalloy@town.westborough.ma.us | bantonioli@town.westborough.ma.us | Robert.Bostwick@state.ma.us | rlarson@umass.edu
2017-10-13 | All Results sent | WestfordPS | WESTFORD | Kathleen | Auth | Director of School Finance | 978-692-5560 x 2106 | 23 Depot St., Westford, MA 01776 | kauth@westfordk12.us | jross@westfordma.gov | scronin@westfordma.gov | Thomas.Mahin@state.ma.us | yaskmenow1983@gmail.com | Kathleen, Huntley, Principal, Abbot Elementary, khuntley@westfordk12.us ¦ John, Emanouil, Head Custodian, Abbot Elementary, jemanouil@westfordk12.us ¦ Richard, Crocker, Director of Plant Operations, rcrocker@westfordk12.us ¦
2018-04-11 | Out of Program | WeymouthPS | WEYMOUTH | Paula | Magnasco | Coordinator of Health Services, Nurse Leader | 781-337-7500 x 25171 | 1 Wildcat Way, Weymouth MA 02190 | paula.magnasco@weymouthps.org | constituentservices@weymouth.ma.us | kmorse@weymouth.ma.us | Richard.Rondeau@state.ma.us |  | John, Barker, Dir of Maintenance, John. Barker@weymouthps.org ¦
2017-12-04 | All Results sent | WLPS | WILLIAMSTOWN | Jim | O'Brien | Building and Grounds supervisor | 413-458-5707 x 136 | 115 Church St., Williamston, MA 01267 | jobrien@williamstownelementary.org | jhoch@williamstownma.gov | erondeau@williamstownma.gov | Deirdre.Doherty@state.ma.us | vdkiken@comcast.net | Jim, O'Brien, buildings and Grounds supervisor, jobrien@williamstownelementary.org ¦
2017-12-04 | All Results sent | WLPS | LANESBOROUGH | Rick | Paris | Custodial Supervisor | 413-443-0027 | 188 Summer St., Lanesborough, MA 01237 | rparis@lanesboroughschool.org | town.secretary@lanesborough-ma.gov | lfwd@verizon.net | Deirdre.Doherty@state.ma.us | vdkiken@comcast.net | Rick, Paris, custodial supervisor, rparis@lanesboroughschool.org ¦ Marty, McEvoy, Principal, mmcevoy@lanesboroughschool.org ¦
2018-05-23 | Waiting List | Amesbury PS | AMESBURY | Joan | Liporto | Director of Finance and Operations | 978-388-0507 x7019 | 5 Highland Street, Amesbury, MA 01915 | liportoj@amesburyma.gov | asked for email address | masonj@amesburyma.gov | Thomas.Mahin@state.ma.us |  | Norman, Fredette, Facilities Manager, fredetten@amesburyma.gov ¦
2018-05-23 | Waiting List | Weston PS | WESTON | Gary | Jarobski | Director of Facilities | 781-786-5270 | 89 Wellesley Street, Weston, MA 02493 | jarobskig@weston.org | vanderclock.d@westonmass.org | cullen.t@westonmass.org | Thomas.Mahin@state.ma.us |  | Gary , Jarobski, Director of Facilities Townwide, jarobskig@weston.org ¦ Tim, deMartin, Deputy Director of Facilities Townwide, demartint@weston.org ¦ Robert, Lager, Head Custodian, lagerr@weston.org ¦
2018-05-23 | Waiting List | St Vincent's Home | FALL RIVER | Paul | Michael | Director of Systems and Operations, Saint Vincent’s | 508-235-3364 | 2425 Highland Avenue, Fall River, MA 02720 | pmichael@stvincentshome.org | mayor@fallriverma.org | gouillette@fallriverma.org | Richard.Rondeau@state.ma.us |  | Paul , Michael, Director of Systems and Operations, pmichael@stvincentshome.org ¦
2018-05-23 | Waiting List | NMRSD | PEPPERELL | Andrea | Royer | Secretary | 978-743-4986 | 45 Main Street, Pepperell, MA 01463 | aroyer@nmrsd.org | mandrews@town.pepperell.ma.us | jjordan@town.pepperell.ma.us | Robert.Bostwick@state.ma.us |  | Al, Beauchemin, Day Lead Custodian, abeauchemin@nmrsd.org ¦ Rich, Carlson, Maintenance, rcarlson@nmrsd.org ¦

## Stats
2017-2018 Statistics |  | Assistance
Number of facilities w/ results | 162 | Full sampling | 40
Number of facilities w/ sample plans | 170 | Follow up | 6
Number of facilities applied to program | 199 | None | 1
Number of facilities done sampling | 162 | EECF | 37
Average number of samples/facility | 69.4059 | No response | 5
Maximum number of samples/ facility | 214 | Out of program | 6
Minimum number of samples/ facility | 6 | Total | 58
Total number of samples | 11799
Total number of samples taken so far | 11131 | Districts
|  | IM completed | 39
|  | IM scheduled | 0
Facilities
|  | PWS | 14
|  | MWRA | 23
2016-2017 Satistics |  | Sampling Plan | 170
Number of schools w/ sample plans | 817 | Sampling done | 162 | 162
Number of schools in program | 894 | Sampling Date | 162
Number of schools done sampling | 818 | sample plan, not sampled yet | 8
Number of schools w/ results | 817 | Results Sent | 162
Average number of samples/school | 68.9445 | Facilities >Pb | 100 | 61.73%
Minimum number of samples/ school | 2 | Facilities >Cu | 63 | 38.89%
Maximum number of samples/ school | 431 | Facilities 0 exceedance | 48 | 29.63%
Total number of samples paid by UMass | 50396
Total number of samples | 55914 | # Towns | 81